## Exhibit
New England Transmission Owner Asset Condition Project Forecast
NOTE: "Under Evaluation" and "Under Development" projects are provided for illustrative purposes only and are not necessarily indicative of actual projects and identified needs.
Project Stages
Presented to PAC – Project has been presented to PAC and is listed on June 2025 Asset Condition List
Under Development – Project planning is underway; project scope and conceptual cost estimates are currently being developed; Cost Category information available
Under Evaluation – Currently being evaluated for possible asset condition project, but no formal scope/cost estimates have been developed; Planning Horizon information available
[9 empty] | June 2025 Asset Condition List Data |  |  |  | Under Development
Project Stage | AC Forecast ID Number | ACL ID | Line Number or Substation Name | kV | Primary Equipment Owner | State | Current Asset Condition | Anticipated Solution | PAC Presentation Date | Status (Concept, Proposed, Planned, Under Construction) | Estimated Cost | Estimated ISD | Anticipated PAC Presentation Date | Cost Category | Planning Horizon | Year Added to AC Forecast
Presented to PAC | ES-001 | 338 | Millstone Substation | 345 | Eversource | CT | Aging substation infrastructure, breakers, transformer/autotransformer, relays and/or control house | Replace circuit breakers | 2022-05-18 | Under Construction | 25950000 | 2029 |  |  |  | 2024 or earlier
Presented to PAC | ES-002 | 352 | 1637/1720 and 1714/1720/1222 | 115 | Eversource | CT | Degradation of structures. conductor, shield wire and/or hardware | Replace structures. conductor, shield wire and/or hardware | 2022-11-15 | Under Construction | 159590000 | 2027 |  |  |  | 2024 or earlier
Presented to PAC | ES-003 | 356 | 348 | 345 | Eversource | CT | Degradation of structures. conductor, shield wire and/or hardware | Replace structures. conductor, shield wire and/or hardware | 2022-09-21 | Under Construction | 8400000 | 2025 |  |  |  | 2024 or earlier
Presented to PAC | ES-004 | 357 | 1772 | 115 | Eversource | CT | Degradation of structures. conductor, shield wire and/or hardware | Replace structures. conductor, shield wire and/or hardware | 2022-09-21 | Under Construction | 20730000 | 2026 |  |  |  | 2024 or earlier
Presented to PAC | ES-005 | 358 | 3041 | 345 | Eversource | CT | Degradation of structures. conductor, shield wire and/or hardware | Replace structures. conductor, shield wire and/or hardware | 2022-10-19 | Under Construction | 32182000 | 2025 |  |  |  | 2024 or earlier
Presented to PAC | ES-006 | 359 | 362 | 345 | Eversource | CT | Degradation of structures. conductor, shield wire and/or hardware | Replace structures. conductor, shield wire and/or hardware | 2022-11-15 | Under Construction | 19163000 | 2025 |  |  |  | 2024 or earlier
Presented to PAC | ES-007 | 373 | 1483, 1545,1580, 1710, 1730, Devon Substation | 115 | Eversource | CT | Degradation of structures. conductor, shield wire and/or hardware | Replace structures. conductor, shield wire and/or hardware | 2023-02-15 | Planned | 41110000 | 2026 |  |  |  | 2024 or earlier
Presented to PAC | ES-008 | 375 | 1142, 1319, 1403, 1580, 1808, Towantic Substation, Christian Rd Substation, Beacon Falls Substation, South Naugatuck Substation | 115 | Eversource | CT | Degradation of structures. conductor, shield wire and/or hardware | Replace structures. conductor, shield wire and/or hardware | 2023-02-15 | Under Construction | 101163000 | 2026 |  |  |  | 2024 or earlier
Presented to PAC | ES-009 | 377 | 376 | 345 | Eversource | CT | Degradation of structures. conductor, shield wire and/or hardware | Replace structures. conductor, shield wire and/or hardware | 2023-03-16 | Under Construction | 9020000 | 2026 |  |  |  | 2024 or earlier
Presented to PAC | ES-010 | 412 | 1704 | 115 | Eversource | CT | Deterioration of vaults/ducts, water leaks | Replace HPFF lines with XLPE cables and install new manholes | 2023-06-15 | Under Construction | 178006000 | 2026 |  |  |  | 2024 or earlier
Presented to PAC | ES-011 | 413 | 364 | 345 | Eversource | CT | Degradation of structures. conductor, shield wire and/or hardware | Replace structures. conductor, shield wire and/or hardware | 2023-07-27 | Under Construction | 13398000 | 2025 |  |  |  | 2024 or earlier
Presented to PAC | ES-012 | 414 | 348 | 345 | Eversource | CT | Degradation of structures. conductor, shield wire and/or hardware | Replace structures. conductor, shield wire and/or hardware | 2023-07-27 | Under Construction | 9701000 | 2025 |  |  |  | 2024 or earlier
Presented to PAC | ES-013 | 416 | Southington Substation | 115 | Eversource | CT | Aging substation infrastructure, breakers, transformer/autotransformer, relays and/or control house | Relay upgrades | 2023-08-16 | Under Construction | 13850000 | 2026 |  |  |  | 2024 or earlier
Presented to PAC | ES-014 | 423 | 1722 | 115 | Eversource | CT | Deterioration of vaults/ducts, water leaks | Replace HPFF lines with XLPE cables and install new manholes | 2023-06-15 | Under Construction | 136438000 | 2026 |  |  |  | 2024 or earlier
Presented to PAC | ES-015 | 431 | 362, 376, 1773 | 115 | Eversource | CT | Degradation of structures. conductor, shield wire and/or hardware | Replace structures. conductor, shield wire and/or hardware | 2024-01-18 | Planned | 43600000 | 2026 |  |  |  | 2024 or earlier
Presented to PAC | ES-016 | 432 | 362, 376, 1772 | 115 | Eversource | CT | Degradation of structures. conductor, shield wire and/or hardware | Replace structures. conductor, shield wire and/or hardware | 2024-01-18 | Under Construction | 14748000 | 2025 |  |  |  | 2024 or earlier
Presented to PAC | ES-017 | 435 | NERC CIP-014 - Physical Security Upgrades - Round2/Site 1 | REDACTED | Eversource | CT | CIP-014 Physical Security Upgrades | CIP-014 Physical Security Upgrades | 2016-07-18 | Under Construction | 2213000 | 2026 |  |  |  | 2024 or earlier
Presented to PAC | ES-018 | 441 | NERC CIP-014 - Physical Security Upgrades - Round2/Site 3 | REDACTED | Eversource | CT | CIP-014 Physical Security Upgrades | CIP-014 Physical Security Upgrades | 2016-07-18 | Under Construction | 2180000 | 2027 |  |  |  | 2025
Presented to PAC | ES-019 | 442 | NERC CIP-014 - Physical Security Upgrades - Round2/Site 2 | REDACTED | Eversource | CT | CIP-014 Physical Security Upgrades | CIP-014 Physical Security Upgrades | 2016-07-18 | Under Construction | 2220000 | 2026 |  |  |  | 2025
Presented to PAC | ES-020 | 450 | Manchester Substation | 345 | Eversource | CT | Aging substation infrastructure, breakers, transformer/autotransformer, relays and/or control house | Replace circuit breakers | 2024-09-18 | Under Construction | 18315000 | 2027 |  |  |  | 2024 or earlier
Presented to PAC | ES-021 | 459 | 387 | 115 | Eversource | CT | Degradation of structures. conductor, shield wire and/or hardware | Replace structures. conductor, shield wire and/or hardware | 2024-11-20 | Planned | 9812000 | 2025 |  |  |  | 2024 or earlier
Presented to PAC | ES-022 | 44 | Mystic #250 Substation | 115 | Eversource | MA | Aging substation infrastructure, breakers, transformer/autotransformer, relays and/or control house | Installation of new 115-kV relay and control enclosure with new relay systems and upgrade of existing 115-kV protection system | 2017-06-21 | Under Construction | 41113000 | 2028 |  |  |  | 2024 or earlier
Presented to PAC | ES-023 | 90 | Canal #980 Substation | 345/115 | Eversource | MA | BPS Separation and Asset Condition Project | Installation of new 345-kV relay and control enclosure with new relay systems and upgrade of existing 115-kV protection system | 2018-06-13 | Under Construction | 41237000 | 2025 |  |  |  | 2024 or earlier
Presented to PAC | ES-024 | 250 | 1231/1242 | 115 | Eversource | MA | Degradation of structures. conductor, shield wire and/or hardware | Replace structures. conductor, shield wire and/or hardware | 2022-08-24 | Under Construction | 158504000 | 2025 |  |  |  | 2024 or earlier
Presented to PAC | ES-025 | 293 | Ludlow 19S Substation | 345/115 | Eversource | MA | BPS Separation and Asset Condition Project | Installation of new 345-kV relay and control enclosure with new relay systems and upgrade of existing 115-kV protection system | 2021-02-17 | Under Construction | 61520000 | 2026 |  |  |  | 2024 or earlier
Presented to PAC | ES-026 | 297 | 282-520 & 282-521 | 115 | Eversource | MA | Degradation of pipes and underground conductor | Rebuild lines with LPP, repair infrastructure | 2021-07-22 | Under Construction | 69598000 | 2026 |  |  |  | 2024 or earlier
Presented to PAC | ES-027 | 315 | 191 | 115 | Eversource | MA | Degradation of structures. conductor, shield wire and/or hardware | Replace structures. conductor, shield wire and/or hardware | 2021-12-15 | Under Construction | 27840000 | 2026 |  |  |  | 2024 or earlier
Presented to PAC | ES-028 | 317 | Edgar Station #150 Substation | 115 | Eversource | MA | Failing brown glass insulators | Replace brown glass insulators and additional aging substation components | 2021-12-15 | Under Construction | 4000000 | 2025 |  |  |  | 2024 or earlier
Presented to PAC | ES-029 | 421 | NERC CIP-014 - Physical Security Upgrades - Round 1 | REDACTED | Eversource | MA | CIP-014 Physical Security Upgrades | CIP-014 Physical Security Upgrades | 2016-07-13 | Under Construction | 121092000 | 2025 |  |  |  | 2024 or earlier
Presented to PAC | ES-030 | 458 | 1356 (old 1525) | 115 | Eversource | MA | Degradation of structures. conductor, shield wire and/or hardware | Replace structures. conductor, shield wire and/or hardware | 2024-11-20 | Planned | 5300000 | 2025 |  |  |  | 2024 or earlier
Presented to PAC | ES-031 | 465 | NERC CIP-014 - Physical Security Upgrades - Round2/ EMA Site 1 | REDACTED | Eversource | MA | CIP-014 Physical Security Upgrades | CIP-014 Physical Security Upgrades | 2016-07-18 | Planned | 1747000 | 2025 |  |  |  | 2025
Presented to PAC | ES-032 | 466 | NERC CIP-014 - Physical Security Upgrades - Round2/EMA Site 4 | REDACTED | Eversource | MA | CIP-014 Physical Security Upgrades | CIP-014 Physical Security Upgrades | 2016-07-18 | Planned | 3384000 | 2025 |  |  |  | 2025
Presented to PAC | ES-033 | 470 | 148/522X/Y | 115 | Eversource | MA | Deterioration of vaults/ducts, water leaks | Replace HPFF lines with XLPE cables and install new manholes | 2025-02-28 | Concept | TBD | TBD |  |  |  | 2024 or earlier
Presented to PAC | ES-034 | 471 | 329-520/521 | 115 | Eversource | MA | Deterioration of vaults/ducts, water leaks | Replace HPFF lines with XLPE cables and install new manholes | 2025-02-28 | Concept | TBD | TBD |  |  |  | 2024 or earlier
Presented to PAC | ES-035 | 472 | 329-512/513 | 115 | Eversource | MA | Deterioration of vaults/ducts, water leaks | Replace HPFF lines with XLPE cables and install new manholes | 2025-02-28 | Concept | TBD | TBD |  |  |  | 2025
Presented to PAC | ES-036 | 473 | 346/365 | 345 | Eversource | MA | Deterioration of vaults/ducts, water leaks | Replace HPFF lines with XLPE cables and install new manholes | 2025-02-28 | Concept | TBD | TBD |  |  |  | 2024 or earlier
Presented to PAC | ES-037 | 474 | 496-528/529 | 115 | Eversource | MA | Deterioration of vaults/ducts, water leaks | Replace HPFF lines with XLPE cables and install new manholes | 2025-02-28 | Concept | TBD | TBD |  |  |  | 2024 or earlier
Presented to PAC | ES-038 | 475 | 385-510/511 | 115 | Eversource | MA | Deterioration of vaults/ducts, water leaks | Replace HPFF lines with XLPE cables and install new manholes | 2025-02-28 | Concept | TBD | TBD |  |  |  | 2024 or earlier
Presented to PAC | ES-039 | 476 | 351/358 | 345 | Eversource | MA | Deterioration of vaults/ducts, water leaks | Replace HPFF lines with XLPE cables and install new manholes | 2025-02-28 | Concept | TBD | TBD |  |  |  | 2024 or earlier
Presented to PAC | ES-040 | 477 | 514-510/511 | 115 | Eversource | MA | Deterioration of vaults/ducts, water leaks | Replace HPFF lines with XLPE cables and install new manholes | 2025-02-28 | Concept | TBD | TBD |  |  |  | 2024 or earlier
Presented to PAC | ES-041 | 478 | 514-512/513 | 115 | Eversource | MA | Deterioration of vaults/ducts, water leaks | Replace HPFF lines with XLPE cables and install new manholes | 2025-02-28 | Concept | TBD | TBD |  |  |  | 2024 or earlier
Presented to PAC | ES-042 | 479 | 329-530/531 | 115 | Eversource | MA | Deterioration of vaults/ducts, water leaks | Replace HPFF lines with XLPE cables and install new manholes | 2025-02-28 | Concept | TBD | TBD |  |  |  | 2024 or earlier
Presented to PAC | ES-043 | 480 | 385-512/513 | 115 | Eversource | MA | Deterioration of vaults/ducts, water leaks | Replace HPFF lines with XLPE cables and install new manholes | 2025-02-28 | Concept | TBD | TBD |  |  |  | 2025
Presented to PAC | ES-044 | 481 | 211-514X | 115 | Eversource | MA | Degradation of pipes and underground conductor | Reconductor or rebuild lines | 2025-02-28 | Concept | TBD | TBD |  |  |  | 2024 or earlier
Presented to PAC | ES-045 | 482 | 423-515 | 115 | Eversource | MA | Deterioration of vaults/ducts, water leaks | Replace HPFF lines with XLPE cables and install new manholes | 2025-02-28 | Concept | TBD | TBD |  |  |  | 2024 or earlier
Presented to PAC | ES-046 | 483 | 488-518XY | 115 | Eversource | MA | Deterioration of vaults/ducts, water leaks | Replace HPFF lines with XLPE cables and install new manholes | 2025-02-28 | Concept | TBD | TBD |  |  |  | 2024 or earlier
Presented to PAC | ES-047 | 349 | Scobie Pond Substation | 345 | Eversource | NH | Aging substation infrastructure, breakers, transformer/autotransformer, relays and/or control house | Replace and install new secondary trench system, and expand control house | 2022-06-15 | Under Construction | 19652000 | 2026 |  |  |  | 2024 or earlier
Presented to PAC | ES-048 | 351 | Greggs Substation | 115 | Eversource | NH | Aging substation infrastructure, breakers, transformer/autotransformer, relays and/or control house | Rebuild substation as a breaker and one half scheme | 2022-10-15 | Under Construction | 72193000 | 2025 |  |  |  | 2024 or earlier
Presented to PAC | ES-049 | 387 | Q195 | 115 | Eversource | NH | Degradation of structures. conductor, shield wire and/or hardware | Replace structures. conductor, shield wire and/or hardware | 2023-05-18 | Proposed | 100000000 | 2028 |  |  |  | 2024 or earlier
Presented to PAC | ES-050 | 388 | U199 | 115 | Eversource | NH | Degradation of structures. conductor, shield wire and/or hardware | Replace structures. conductor, shield wire and/or hardware | 2023-05-18 | Under Construction | 70938000 | 2026 |  |  |  | 2024 or earlier
Presented to PAC | ES-051 | 406 | A164 | 115 | Eversource | NH | Degradation of structures. conductor, shield wire and/or hardware | Replace structures. conductor, shield wire and/or hardware | 2023-06-15 | Under Construction | 62446000 | 2026 |  |  |  | 2024 or earlier
Presented to PAC | ES-052 | 409 | G146 | 115 | Eversource | NH | Degradation of structures. conductor, shield wire and/or hardware | Replace structures. conductor, shield wire and/or hardware | 2023-06-15 | Under Construction | 53586000 | 2026 |  |  |  | 2024 or earlier
Presented to PAC | ES-053 | 410 | I158 | 115 | Eversource | NH | Degradation of structures. conductor, shield wire and/or hardware | Replace structures. conductor, shield wire and/or hardware | 2023-06-15 | Under Construction | 25438000 | 2025 |  |  |  | 2024 or earlier
Presented to PAC | ES-054 | 411 | Deerfield Substation | 345/115 | Eversource | NH | Aging substation infrastructure, breakers, transformer/autotransformer, relays and/or control house | Relay upgrades | 2023-06-16 | Under Construction | 7185000 | 2026 |  |  |  | 2024 or earlier
Presented to PAC | ES-055 | 444 | X178 | 115 | Eversource | NH | Degradation of structures. conductor, shield wire and/or hardware | Replace structures. conductor, shield wire and/or hardware | 2024-02-28 | Proposed | 384600000 | 2029 |  |  |  | 2024 or earlier
Presented to PAC | ES-056 | 445 | Campville Substation | 115 | Eversource | NH | Aging substation infrastructure, breakers, transformer/autotransformer, relays and/or control house | Relay upgrades | 2024-06-20 | Under Construction | 5067000 | 2025 |  |  |  | 2025
Presented to PAC | ES-057 | 451 | Amherst Substation | 345 | Eversource | NH | Aging substation infrastructure, breakers, transformer/autotransformer, relays and/or control house | Replace circuit breakers | 2024-09-18 | Under Construction | 10268000 | 2027 |  |  |  | 2024 or earlier
Presented to PAC | CMP-001 | 457 | 396/3001 | 345 | MEPCO | ME | Asset Condition structure replacement program | Replace structures. conductor, shield wire and/or hardware | 2024-06-01 | Under Construction | 344380000 | 2039 |  |  |  | 2024 or earlier
Presented to PAC | NEP-001 | 354 | Maplewood Substation | 115 | New England Power | MA | Aging substation infrastructure, breakers, transformer/autotransformer, relays and/or control house | Partial rebuild substation | 2023-01-19 | Under Construction | 6170000 | 2026 |  |  |  | 2024 or earlier
Presented to PAC | NEP-002 | 294 | Millbury 2 Substation | 115 | New England Power | MA | Aging substation infrastructure, breakers, transformer/autotransformer, relays and/or control house | Partial rebuild substation | 2021-05-19 | Under Construction | 39877000 | 2026 |  |  |  | 2024 or earlier
Presented to PAC | NEP-003 | 439 | O-141/P-142 | 115 | New England Power | MA | Degradation of structures. conductor, shield wire and/or hardware | Replace structures. conductor, shield wire and/or hardware | 2024-05-15 | Under Construction | 39013470 | 2025 |  |  |  | 2024 or earlier
Presented to PAC | NEP-004 | 419 | S8 | 115 | New England Power | MA | Degradation of structures. conductor, shield wire and/or hardware | Replace structures. conductor, shield wire and/or hardware | 2023-07-25 | Under Construction | 66677000 | 2026 |  |  |  | 2024 or earlier
Presented to PAC | NEP-005 | 437 | 339/349 | 345 | New England Power | MA | Degradation of structures. conductor, shield wire and/or hardware | Replace structures. conductor, shield wire and/or hardware | 2024-04-18 | Under Construction | 72591000 | 2025 |  |  |  | 2024 or earlier
Presented to PAC | NEP-006 | 328 | Bridgewater Substation | 345/115 | New England Power | MA | Aging substation infrastructure, breakers, transformer/autotransformer, relays and/or control house | Partial rebuild substation | 2022-04-28 | Planned | 37795735 | 2028 |  |  |  | 2024 or earlier
Presented to PAC | NEP-007 | 336 | Tewksbury Sub 22 Substation | 230/115 | New England Power | MA | Aging substation infrastructure, breakers, transformer/autotransformer, relays and/or control house | Partial rebuild substation | 2022-08-24 | Planned | 62180000 | 2029 |  |  |  | 2024 or earlier
Presented to PAC | NEP-008 | 384 | Shutesbury Substation | 69 | New England Power | MA | Aging substation infrastructure, breakers, transformer/autotransformer, relays and/or control house | Full substation rebuild | 2023-03-16 | Proposed | 8900000 | 2028 |  |  |  | 2024 or earlier
Presented to PAC | NEP-009 | 236 | Deerfield #4 Substation | 115/69 | New England Power | MA | Aging substation infrastructure, breakers, transformer/autotransformer, relays and/or control house | Full substation rebuild | 2020-04-23 | Concept |  | 2030 |  |  |  | 2024 or earlier
Presented to PAC | NEP-010 | 420 | V5/U6 | 115 | New England Power | MA | Degradation of structures. conductor, shield wire and/or hardware | Replace structures. conductor, shield wire and/or hardware | 2023-07-25 | Proposed | 131980000 | 2029 |  |  |  | 2024 or earlier
Presented to PAC | NEP-011 | 400 | Adams Substation | 115/69 | New England Power | MA | Aging substation infrastructure, breakers, transformer/autotransformer, relays and/or control house | Relocate substation | 2023-05-12 | Proposed | 60985070 | 2030 |  |  |  | 2024 or earlier
Presented to PAC | NEP-012 | 337 | E-5/F-6 | 69 | New England Power | MA | Degradation of structures. conductor, shield wire and/or hardware | Replace structures. conductor, shield wire and/or hardware | 2022-06-15 | Concept |  | 2030 |  |  |  | 2024 or earlier
Presented to PAC | NEP-013 | 447 | W-149 | 115 | New England Power | MA | Degradation of structures. conductor, shield wire and/or hardware | Replace structures. conductor, shield wire and/or hardware | 2024-05-24 | Proposed | 345000000 | 2030 |  |  |  | 2025
Presented to PAC | NEP-014 | 460 | B-154/C-155 | 115 | New England Power | MA | Degradation of structures. conductor, shield wire and/or hardware | Degradation of structures. conductor, shield wire and/or hardware | 2024-10-01 | Proposed | 46653000 | 2027 |  |  |  | 2025
Presented to PAC | NEP-015 | 433 | A-201/B-202 | 230 | New England Power | MA | Degradation of structures. conductor, shield wire and/or hardware | Replace structures. conductor, shield wire and/or hardware | 2024-01-11 | Concept |  | 2031 |  |  |  | 2024 or earlier
Presented to PAC | NEP-016 | 438 | E-205E | 230 | New England Power | MA | Rebuild to 345kV design | Replace structures. conductor, shield wire and/or hardware | 2024-04-11 | Concept |  | 2033 |  |  |  | 2024 or earlier
Presented to PAC | NEP-017 | 462 | 337 | 345 | New England Power | MA | Degradation of structures. conductor, shield wire and/or hardware | Replace structures. conductor, shield wire and/or hardware | 2024-12-18 | Proposed | 217448000 | 2032 |  |  |  | 2024 or earlier
Presented to PAC | NEP-018 | 467 | A-179 | 115 | New England Power | MA | Degradation of structures. conductor, shield wire and/or hardware | Replace structures. conductor, shield wire and/or hardware | 2025-06-16 | Planned | 11960000 | 2027 |  |  |  | 2024 or earlier
Presented to PAC | NEP-019 | 468 | D-156 | 115 | New England Power | MA | Degradation of structures. conductor, shield wire and/or hardware | Replace structures. conductor, shield wire and/or hardware | 2025-03-19 | Planned | 19005000 | 2026 |  |  |  | 2024 or earlier
Presented to PAC | NEP-020 | 455 | Westminster Switch Tower | 69 | New England Power | MA | Aging substation infrastructure, breakers, transformer/autotransformer, relays and/or control house | Partial rebuild substation | 2024-12-18 | Planned | 7900000 | 2026 |  |  |  | 2024 or earlier
Presented to PAC | NEP-021 | 452 | 302 | 345 | New England Power | MA | Degradation of structures. conductor, shield wire and/or hardware | Replace structures. conductor, shield wire and/or hardware | 2024-09-18 | Under Construction | 19360000 | 2025 |  |  |  | 2024 or earlier
Presented to PAC | NEP-022 | 461 | 338 | 345 | New England Power | MA | Degradation of structures. conductor, shield wire and/or hardware | Replace structures. conductor, shield wire and/or hardware | 2024-11-20 | Proposed | 53520000 | 2030 |  |  |  | 2024 or earlier
Presented to PAC | NEP-023 | 449 | 313/343 | 345 | New England Power | MA | Degradation of structures. conductor, shield wire and/or hardware | Replace structures. conductor, shield wire and/or hardware | 2024-08-21 | Planned | 78820000 | 2025 |  |  |  | 2024 or earlier
Presented to PAC | NEP-024 | 448 | Brayton Point Substation | 345/115 | New England Power | MA | Aging substation infrastructure, breakers, transformer/autotransformer, relays and/or control house | Partial rebuild substation | 2024-08-21 | Planned | 46578000 | 2031 |  |  |  | 2024 or earlier
Presented to PAC | NEP-025 | 463 | Sandy Pond Substation | 345 | New England Power | MA | Aging substation infrastructure, breakers, transformer/autotransformer, relays and/or control house | Partial rebuild substation | 2024-12-18 | Planned | 16196000 | 2028 |  |  |  | 2024 or earlier
Presented to PAC | NEP-026 | 385 | E-131 | 115 | New England Power | MA/VT | Degradation of structures. conductor, shield wire and/or hardware | Replace structures. conductor, shield wire and/or hardware | 2023-04-20 | Proposed | 138300000 | 2027 |  |  |  | 2024 or earlier
Presented to PAC | NEP-027 | 237 | A-1/B-2 | 69 | New England Power | MA/VT | Degradation of structures. conductor, shield wire and/or hardware | Replace structures. conductor, shield wire and/or hardware | 2022-07-14 | Planned | 414730000 | 2030 |  |  |  | 2024 or earlier
Presented to PAC | NEP-028 | 438 | E-205W | 230 | New England Power | MA/VT | Rebuild to 345kV design | Replace structures. conductor, shield wire and/or hardware | 2024-04-11 | Concept |  | 2033 |  |  |  | 2024 or earlier
Presented to PAC | NEP-029 | 235 | Vernon Substation | 69 | New England Power | NH | Aging substation infrastructure, breakers, transformer/autotransformer, relays and/or control house | Relocate substation | 2021-11-17 | Planned | 39690000 | 2029 |  |  |  | 2024 or earlier
Presented to PAC | NEP-030 | 308 | Moore 20 Substation | 230/115 | New England Power | NH | Aging substation infrastructure, breakers, transformer/autotransformer, relays and/or control house | Partial rebuild substation | 2021-09-22 | Planned | 49307000 | 2029 |  |  |  | 2024 or earlier
Presented to PAC | NEP-031 | 440 | W-149 | 115 | New England Power | NH/VT | Degradation of structures. conductor, shield wire and/or hardware | Replace structures. conductor, shield wire and/or hardware | 2024-05-24 | Proposed | 2000000 | 2030 |  |  |  | 2024 or earlier
Presented to PAC | RIE-001 | 99 | R-144, Q-143S, & V-148N | 115 | Rhode Island Energy | RI | NPCC Directory # 1 Protection Modification - Phase 4. | Upgrade line protection to dual high speed systems. | 2017-12-01 | Concept | 5100000 | 2025 |  |  |  | 2024 or earlier
Presented to PAC | RIE-002 | 430 | E-183W | 115 | Rhode Island Energy | RI | Degradation of structures. conductor, shield wire and/or hardware | Replace structures. conductor, shield wire and/or hardware | 2023-10-01 | Proposed | 10600000 | 2026 |  |  |  | 2024 or earlier
Presented to PAC | RIE-003 | 426 | S-171N | 115 | Rhode Island Energy | RI | Degradation of structures. conductor, shield wire and/or hardware | Replace structures. conductor, shield wire and/or hardware | 2023-10-01 | Planned | 14633000 | 2026 |  |  |  | 2024 or earlier
Presented to PAC | RIE-004 | 427 | T-172N | 115 | Rhode Island Energy | RI | Degradation of structures. conductor, shield wire and/or hardware | Replace structures. conductor, shield wire and/or hardware | 2023-10-01 | Planned | 14633000 | 2026 |  |  |  | 2024 or earlier
Presented to PAC | UI-001 | 22 | Pequannock | 115 | United Illuminating Company | CT | Coastal Substation Flood Mitigation Study Project | Relocate substation | 2015-09-01 | Under Construction | 109946055 | 2025 |  |  |  | 2024 or earlier
Presented to PAC | UI-002 | 91 | 8809A-2 | 115 | United Illuminating Company | CT | Railroad Corridor Transmission Line Asset Condition Upgrades | Rebuild in new location with new monopoles, conductor and shield wire | 2018-06-01 | Planned | 22075393 | 2027 |  |  |  | 2024 or earlier
Presented to PAC | UI-003 | 151 | 8809B-2 | 115 | United Illuminating Company | CT | Railroad Corridor Transmission Line Asset Condition Upgrades | Rebuild in new location with new monopoles, conductor and shield wire | 2018-06-01 | Planned | 22075393 | 2027 |  |  |  | 2024 or earlier
Presented to PAC | UI-004 | 157 | 8804A | 115 | United Illuminating Company | CT | Railroad Corridor Transmission Line Asset Condition Upgrades | Rebuild in new location with new monopoles, conductor and shield wire | 2018-06-01 | Under Construction | 51810000 | 2026 |  |  |  | 2024 or earlier
Presented to PAC | UI-005 | 239 | 1560-3, 1594, 1808 | 115 | United Illuminating Company | CT | Derby Junction to Ansonia Corridor 115 kV Transmission Upgrades | Replace structures. conductor, shield wire and/or hardware | 2019-10-01 | Under Construction | 70986666 | 2025 |  |  |  | 2024 or earlier
Presented to PAC | UI-006 | 20 | Grand Avenue | 115 | United Illuminating Company | CT | Coastal Substation Flood Mitigation Study Project | Install flood wall | 2015-09-01 | Planned | 41800000 | 2026 |  |  |  | 2024 or earlier
Presented to PAC | UI-007 | 21 | Singer | 345 | United Illuminating Company | CT | Coastal Substation Flood Mitigation Study Project | Install flood wall | 2015-09-01 | Under Construction | 26450000 | 2026 |  |  |  | 2024 or earlier
Presented to PAC | UI-008 | 154 | 91001-1 & 91001-2 | 115 | United Illuminating Company | CT | Railroad Corridor Transmission Line Asset Condition Upgrades | Rebuild in new location with new monopoles, conductor and shield wire | 2018-06-01 | Planned | 47006000 | 2026 |  |  |  | 2024 or earlier
Presented to PAC | UI-009 | 158 | 8804B | 115 | United Illuminating Company | CT | Railroad Corridor Transmission Line Asset Condition Upgrades | Rebuild in new location with new monopoles, conductor and shield wire | 2018-06-01 | Under Construction | 51810000 | 2026 |  |  |  | 2024 or earlier
Presented to PAC | UI-010 | 155 | 88005A-1 | 115 | United Illuminating Company | CT | Railroad Corridor Transmission Line Asset Condition Upgrades | Rebuild in new location with new monopoles, conductor and shield wire | 2018-06-01 | Under Construction | 69080000 | 2027 |  |  |  | 2024 or earlier
Presented to PAC | UI-011 | 156 | 88005B-1 | 115 | United Illuminating Company | CT | Railroad Corridor Transmission Line Asset Condition Upgrades | Rebuild in new location with new monopoles, conductor and shield wire | 2018-06-01 | Under Construction | 69080000 | 2027 |  |  |  | 2024 or earlier
Presented to PAC | UI-012 | 152 | 1130 | 115 | United Illuminating Company | CT | Railroad Corridor Transmission Line Asset Condition Upgrades | Rebuild in new location with new monopoles, conductor and shield wire | 2018-06-01 | Planned | 201231776 | 2028 |  |  |  | 2024 or earlier
Presented to PAC | UI-013 | 153 | 1430 | 115 | United Illuminating Company | CT | Railroad Corridor Transmission Line Asset Condition Upgrades | Rebuild in new location with new monopoles, conductor and shield wire | 2018-06-01 | Planned | 105111619 | 2028 |  |  |  | 2024 or earlier
Presented to PAC | VEP-001 | 456 | Line K19 | 115 | Vermont Electric Power Co | VT | Degradation of structures. conductor, shield wire and/or hardware | Replace structures. conductor, shield wire and/or hardware | 2024-10-23 | Under Construction | 6000000 | 2025 |  |  |  | 2024 or earlier
Presented to PAC | VEP-002 | 305 | Line K42 | 115 | Vermont Electric Power Co | VT | Degradation of structures. conductor, shield wire and/or hardware | Complete line rebuild | 2023-10-19 | Under Construction | 84844000 | 2026 |  |  |  | 2024 or earlier
Presented to PAC | VEP-003 | 331 | Line K32 | 115 | Vermont Electric Power Co | VT | Degradation of structures. conductor, shield wire and/or hardware | Replace structures. conductor, shield wire and/or hardware | 2022-05-12 | Under Construction | 14320000 | 2026 |  |  |  | 2024 or earlier
Presented to PAC | VEP-004 | 383 | Line K43 | 115 | Vermont Electric Power Co | VT | Degradation of structures. conductor, shield wire and/or hardware | Replace structures. conductor, shield wire and/or hardware | 2023-04-14 | Under Construction | 13980000 | 2026 |  |  |  | 2024 or earlier
Presented to PAC | VEP-005 |  | St. Johnsbury substation | 115 | Vermont Electric Power Co | VT | Aging substation infrastructure, breakers, transformer/autotransformer, relays and/or control house | Partial rebuild substation | N/A - Less than $5M PTF | Under Construction | 18437234 | 2026 |  |  |  | 2024 or earlier
Presented to PAC | VEP-006 | 284 | Line K24 | 115 | Vermont Electric Power Co | VT | Degradation of structures. conductor, shield wire and/or hardware | Replace structures. conductor, shield wire and/or hardware | 2021-02-12 | Under Construction | 15240000 | 2027 |  |  |  | 2024 or earlier
Presented to PAC | VEP-007 | 330 | Line K21 | 115 | Vermont Electric Power Co | VT | Degradation of structures. conductor, shield wire and/or hardware | Replace structures. conductor, shield wire and/or hardware | 2022-05-12 | Under Construction | 20550000 | 2027 |  |  |  | 2024 or earlier
Presented to PAC | VEP-008 | 436 | Sand Bar PST | 115 | Vermont Electric Power Co | VT | History of PST issues | Add smart valves device | 2024-02-28 | Planned | 47700000 | 2027 |  |  |  | 2024 or earlier
Presented to PAC | VEP-009 | 332 | Line K50 | 115 | Vermont Electric Power Co | VT | Degradation of structures. conductor, shield wire and/or hardware | Replace structures. conductor, shield wire and/or hardware | 2022-05-12 | Under Construction | 31280000 | 2027 |  |  |  | 2024 or earlier
Under Development | CMP-002 | N/A | S3038 | 345 | CMP | ME | Degradation of structures. conductor, shield wire and/or hardware | Replace structures. conductor, shield wire and/or hardware |  |  |  |  | 2025-08-01 | Group 2: $10-25M | 1 Year | 2024 or earlier
Under Development | CMP-003 | N/A | S207 | 115 | CMP | ME | Degradation of structures. conductor, shield wire and/or hardware | Replace structures. conductor, shield wire and/or hardware |  |  |  |  | 2025-08-01 | Group 2: $10-25M | 1 Year | 2024 or earlier
Under Development | CMP-004 | N/A | S375 | 345 | CMP | ME | Degradation of structures. conductor, shield wire and/or hardware | Replace structures. conductor, shield wire and/or hardware |  |  |  |  | 2025-08-01 | Group 2: $10-25M | 1 Year | 2024 or earlier
Under Development | CMP-005 | N/A | S374 | 345 | CMP | ME | Degradation of structures. conductor, shield wire and/or hardware | Replace structures. conductor, shield wire and/or hardware |  |  |  |  | 2025-08-01 | Group 2: $10-25M | 1 Year | 2024 or earlier
Under Development | CMP-006 | N/A | S385 | 345 | CMP | ME | Degradation of structures. conductor, shield wire and/or hardware | Replace structures. conductor, shield wire and/or hardware |  |  |  |  | 2025-08-01 | Group 2: $10-25M | 1 Year | 2024 or earlier
Under Development | CMP-007 | N/A | S63 | 115 | CMP | ME | Degradation of structures. conductor, shield wire and/or hardware | Replace structures. conductor, shield wire and/or hardware |  |  |  |  | 2025-08-01 | Group 1: $0-10M | 1 Year | 2025
Under Development | CMP-008 | N/A | S200 | 115 | CMP | ME | Degradation of structures. conductor, shield wire and/or hardware | Replace structures. conductor, shield wire and/or hardware |  |  |  |  | 2025-08-01 | Group 1: $0-10M | 1 Year | 2025
Under Development | CMP-009 | N/A | S377 | 345 | CMP | ME | Degradation of structures. conductor, shield wire and/or hardware | Replace structures. conductor, shield wire and/or hardware |  |  |  |  | 2025-08-01 | Group 1: $0-10M | 1 Year | 2025
Under Development | CMP-010 | N/A | S391 | 345 | CMP | ME | Degradation of structures. conductor, shield wire and/or hardware | Replace structures. conductor, shield wire and/or hardware |  |  |  |  | 2025-08-01 | Group 1: $0-10M | 1 Year | 2025
Under Development | CMP-011 | N/A | S392 | 345 | CMP | ME | Degradation of structures. conductor, shield wire and/or hardware | Replace structures. conductor, shield wire and/or hardware |  |  |  |  | 2025-08-01 | Group 1: $0-10M | 1 Year | 2025
Under Development | ES-058 | N/A | 1759 | 115 | Eversource | CT | Degradation of structures. conductor, shield wire and/or hardware | Replace structures. conductor, shield wire and/or hardware |  |  |  |  | 2025-08-01 | Group 2: $10-25M | 2 Year | 2024 or earlier
Under Development | ES-059 | N/A | 1773 | 115 | Eversource | CT | Degradation of structures. conductor, shield wire and/or hardware | Replace structures. conductor, shield wire and/or hardware |  |  |  |  | 2026-06-01 | Group 1: $0-10M | 2 Year | 2024 or earlier
Under Development | ES-060 | N/A | 3403C and 3403D | 345 | Eversource | CT | Installation of stop joints to address overall reliability and enviornental risk of fluid leakage | Installation/replacement of Motor Operated Valves on underground lines |  |  |  |  | 2025-10-01 | Group 2: $10-25M | 2 Year | 2024 or earlier
Under Development | ES-061 | N/A | 1771 , 1670-1, 1670-2 | 115 | Eversource | CT | Degradation of structures. conductor, shield wire and/or hardware | Replace structures. conductor, shield wire and/or hardware |  |  |  |  | 2025-10-01 | Group 4: $100M+ | 3-5 Year | 2024 or earlier
Under Development | ES-062 | N/A | Long Mountain Substation | 345 | Eversource | CT | Aging substation infrastructure and BPS/Directory 4 compliance | BPS/DIR4 upgrades, breaker replacement |  |  |  |  | 2026-03-01 | Group 2: $10-25M | 3-5 Year | 2024 or earlier
Under Development | ES-063 | N/A | Compo Substation | 115 | Eversource | CT | Aging substation infrastructure, breakers, transformer/autotransformer, relays and/or control house | Relay upgrades |  |  |  |  | 2026-03-01 | Group 2: $10-25M | 3-5 Year | 2024 or earlier
Under Development | ES-064 | N/A | 1867-1/1880-1 | 115 | Eversource | CT | Degradation of structures. conductor, shield wire and/or hardware | Replace structures. conductor, shield wire and/or hardware |  |  |  |  | 2026-06-01 | Group 2: $10-25M | 3-5 Year | 2024 or earlier
Under Development | ES-065 | N/A | 1440 | 115 | Eversource | CT | Degradation of structures. conductor, shield wire and/or hardware | Replace structures. conductor, shield wire and/or hardware |  |  |  |  | 2026-09-01 | Group 2: $10-25M | 3-5 Year | 2024 or earlier
Under Development | ES-066 | N/A | Line 1867-2/1880-3 | 115 | Eversource | CT | Degradation of structures. conductor, shield wire and/or hardware | Replace structures. conductor, shield wire and/or hardware |  |  |  |  | 2026-06-01 | Group 3: $25-100M | 3-5 Year | 2024 or earlier
Under Development | ES-067 | N/A | Montville Substation | 345/115 | Eversource | CT | BPS/DIR4 upgrades, preimary and secondary relay upgrades, control house upgrades, etc. | Review of existing control house and primary and secondary protection schemes |  |  |  |  | TBD | Group 3: $25-100M | 3-5 Year | 2024 or earlier
Under Development | ES-068 | N/A | 1028 | 115 | Eversource | CT | Degradation of structures. conductor, shield wire and/or hardware | Replace structures. conductor, shield wire and/or hardware |  |  |  |  | 2026-01-01 | Group 3: $25-100M | 6-10 Year | 2024 or earlier
Under Development | ES-069 | N/A | 1430 | 115 | Eversource | CT | Degradation of structures. conductor, shield wire and/or hardware | Replace structures. conductor, shield wire and/or hardware |  |  |  |  | 2026-01-01 | Group 3: $25-100M | 6-10 Year | 2024 or earlier
Under Development | ES-070 | N/A | 1578 | 115 | Eversource | CT | Degradation of structures. conductor, shield wire and/or hardware | Replace structures. conductor, shield wire and/or hardware |  |  |  |  | 2026-01-01 | Group 3: $25-100M | 6-10 Year | 2024 or earlier
Under Development | ES-071 | N/A | 1146 | 115 | Eversource | CT | Degradation of structures. conductor, shield wire and/or hardware | Replace structures. conductor, shield wire and/or hardware |  |  |  |  | 2026-01-01 | Group 3: $25-100M | 6-10 Year | 2024 or earlier
Under Development | ES-072 | N/A | 1608 | 115 | Eversource | CT | Degradation of structures. conductor, shield wire and/or hardware | Replace structures. conductor, shield wire and/or hardware |  |  |  |  | 2026-01-01 | Group 3: $25-100M | 6-10 Year | 2024 or earlier
Under Development | ES-073 | N/A | Middletown Substation | 115 | Eversource | CT | Aging substation infrastructure, breakers, transformer/autotransformer, relays and/or control house | Relay upgrades |  |  |  |  | TBD | Group 1: $0-10M | 2 Year | 2024 or earlier
Under Development | ES-074 | N/A | North Bloomfield Substation | 345/115 | Eversource | CT | Aging substation infrastructure, breakers, transformer/autotransformer, relays and/or control house | Replace autotransformer |  |  |  |  | TBD | Group 3: $25-100M | 3-5 Year | 2024 or earlier
Under Development | ES-075 | N/A | Millstone Substation | 345/115 | Eversource | CT | BPS/DIR4 upgrades, preimary and secondary relay upgrades, control house upgrades, etc. | Review of existing control house and primary and secondary protection schemes |  |  |  |  | TBD | Group 2: $10-25M | 3-5 Year | 2024 or earlier
Under Development | ES-076 | N/A | Middletown 5A Substation | 115 | Eversource | CT | Aging substation infrastructure, breakers, transformer/autotransformer, relays and/or control house | Relay upgrades |  |  |  |  | TBD | Group 1: $0-10M | 2 Year | 2025
Under Development | ES-077 | N/A | 1207 | 115 | Eversource | CT | Telecom need | OPGW Instalation |  |  |  |  | TBD | Group 1: $0-10M | 3-5 Year | 2025
Under Development | ES-078 | N/A | 65-502 | 115 | Eversource | MA | Degradation of structures. conductor, shield wire and/or hardware | Replace structures. conductor, shield wire and/or hardware |  |  |  |  | 2025-12-01 | Group 2: $10-25M | 3-5 Year | 2024 or earlier
Under Development | ES-079 | N/A | Pilgrim #725 Substation | 345 | Eversource | MA | Aging substation infrastructure and BPS/Directory 4 compliance | BPS/DIR4 upgrades, breaker replacement |  |  |  |  | 2025-11-01 | Group 3: $25-100M | 3-5 Year | 2024 or earlier
Under Development | ES-080 | N/A | 342/355 | 345 | Eversource | MA | Degradation of structures. conductor, shield wire and/or hardware | Replace structures. conductor, shield wire and/or hardware |  |  |  |  | 2026-02-01 | Group 3: $25-100M | 3-5 Year | 2024 or earlier
Under Development | ES-081 | N/A | 325 | 345 | Eversource | MA | Degradation of structures. conductor, shield wire and/or hardware | Replace structures. conductor, shield wire and/or hardware |  |  |  |  | 2025-12-01 | Group 3: $25-100M | 3-5 Year | 2024 or earlier
Under Development | ES-082 | N/A | 331 | 345 | Eversource | MA | Degradation of structures. conductor, shield wire and/or hardware | Replace structures. conductor, shield wire and/or hardware |  |  |  |  | 2025-12-01 | Group 1: $0-10M | 3-5 Year | 2024 or earlier
Under Development | ES-083 | N/A | Holbrook #478 Substation | 115 | Eversource | MA | Failing brown glass insulators | Replace brown glass insulators and additional aging substation components |  |  |  |  | 2026-05-01 | Group 1: $0-10M | 3-5 Year | 2024 or earlier
Under Development | ES-084 | N/A | K Street #385 Substation | 115 | Eversource | MA | Failing brown glass insulators | Replace brown glass insulators and additional aging substation components |  |  |  |  | 2026-05-01 | Group 1: $0-10M | 3-5 Year | 2024 or earlier
Under Development | ES-085 | N/A | Baker St #110 Substation | 115 | Eversource | MA | Failing brown glass insulators | Replace brown glass insulators and additional aging substation components |  |  |  |  | 2026-05-01 | Group 1: $0-10M | 3-5 Year | 2024 or earlier
Under Development | ES-086 | N/A | Ludlow Substation | 345 | Eversource | MA | Aging substation infrastructure, breakers, transformer/autotransformer, relays and/or control house | Replace circuit breakers |  |  |  |  | 2026-02-01 | Group 2: $10-25M | 3-5 Year | 2024 or earlier
Under Development | ES-087 | N/A | 282-507/602 | 115/230 | Eversource | MA | Degradation of structures. conductor, shield wire and/or hardware | Replace structures. conductor, shield wire and/or hardware |  |  |  |  | 2026-03-01 | Group 3: $25-100M | 6-10 Year | 2024 or earlier
Under Development | ES-088 | N/A | Mystic #250 Substation | 115 | Eversource | MA | Failing brown glass insulators | Replace brown glass insulators and additional aging substation components |  |  |  |  | 2026-05-01 | Group 1: $0-10M | 6-10 Year | 2024 or earlier
Under Development | ES-089 | N/A | 65-508 | 115 | Eversource | MA | Degradation of structures. conductor, shield wire and/or hardware | Replace structures. conductor, shield wire and/or hardware |  |  |  |  | 2025-12-01 | Group 1: $0-10M | 3-5 Year | 2025
Under Development | ES-090 | N/A | 389 | 115 | Eversource | MA | Degradation of structures. conductor, shield wire and/or hardware | Replace structures. conductor, shield wire and/or hardware |  |  |  |  | 2025-12-01 | Group 1: $0-10M | 3-5 Year | 2025
Under Development | ES-091 | N/A | North Cambridge #509 Substation | 115 | Eversource | MA | Damaged duct bank and cables | Replace/repair damaged equipment |  |  |  |  | 2025-12-01 | Group 1: $0-10M | TBD | 2025
Under Development | ES-092 | N/A | Northfield Mountain Substation | 345 | Eversource | MA | BPS Separation and Asset Condition Project | Review of existing control house and primary and secondary protection schemes |  |  |  |  | 2025-11-01 | Group 2: $10-25M | 3-5 Year | 2024 or earlier
Under Development | ES-093 | N/A | Mystic #250 Substation | 345/115 | Eversource | MA | BPS/DIR4 upgrades, preimary and secondary relay upgrades, control house upgrades, etc. | Review of existing control house and primary and secondary protection schemes |  |  |  |  | TBD | Group 3: $25-100M | 3-5 Year | 2024 or earlier
Under Development | ES-094 | N/A | K Street #385 Substation | 345/115 | Eversource | MA | BPS/DIR4 upgrades, preimary and secondary relay upgrades, control house upgrades, etc. | Review of existing control house and primary and secondary protection schemes |  |  |  |  | TBD | Group 2: $10-25M | 3-5 Year | 2024 or earlier
Under Development | ES-095 | N/A | Canal #980 Substation | 345/115 | Eversource | MA | Aging substation infrastructure, breakers, transformer/autotransformer, relays and/or control house | Replace autotransformer |  |  |  |  | TBD | Group 2: $10-25M | 3-5 Year | 2024 or earlier
Under Development | ES-096 | N/A | Canal #980 Substation | 345/115 | Eversource | MA | Aging substation infrastructure, breakers, transformer/autotransformer, relays and/or control house | Replace autotransformer |  |  |  |  | TBD | Group 2: $10-25M | 3-5 Year | 2024 or earlier
Under Development | ES-097 | N/A | Barnstable STA 958 | 115 | Eversource | MA | Degradation of Mobile Cap Bank | Mobile Cap Bank Replacement |  |  |  |  | TBD | TBD | 3-5 Year | 2025
Under Development | ES-098 | N/A | Wing Lane STA 624 | 115 | Eversource | MA | Degradation of Mobile Cap Bank | Mobile Cap Bank Replacement |  |  |  |  | TBD | TBD | 3-5 Year | 2025
Under Development | ES-099 | N/A | Scobie Pond Substation | 115 | Eversource | NH | Aging substation infrastructure, breakers, transformer/autotransformer, relays and/or control house | Relay upgrades |  |  |  |  | 2025-06-01 | Group 1: $0-10M | 2 Year | 2024 or earlier
Under Development | ES-100 | N/A | Fitzwilliam Substation | 345 | Eversource | NH | Aging substation infrastructure, breakers, transformer/autotransformer, relays and/or control house | Replace circuit breakers |  |  |  |  | 2026-02-01 | Group 1: $0-10M | 3-5 Year | 2024 or earlier
Under Development | ES-101 | N/A | Newington Substation | 345/115 | Eversource | NH | BPS Separation and Asset Condition Project | Review of existing control house and primary and secondary protection schemes |  |  |  |  | 2026-05-01 | Group 2: $10-25M | 3-5 Year | 2024 or earlier
Under Development | ES-102 | N/A | B172 | 115 | Eversource | NH | Degradation of structures. conductor, shield wire and/or hardware | Replace structures. conductor, shield wire and/or hardware |  |  |  |  | 2025-12-01 | Group 3: $25-100M | 2 Year | 2024 or earlier
Under Development | ES-103 | N/A | T198 | 115 | Eversource | NH | Degradation of structures. conductor, shield wire and/or hardware | Replace structures. conductor, shield wire and/or hardware |  |  |  |  | 2025-07-01 | Group 2: $10-25M | 2 Year | 2024 or earlier
Under Development | ES-104 | N/A | A152 | 115 | Eversource | NH | Degradation of structures. conductor, shield wire and/or hardware | Degradation of structures. conductor, shield wire and/or hardware |  |  |  |  | 2025-12-01 | Group 3: $25-100M | 3-5 Year | 2025
Under Development | ES-105 | N/A | S153 | 115 | Eversource | NH | Degradation of structures. conductor, shield wire and/or hardware | Replace structures. conductor, shield wire and/or hardware |  |  |  |  | 2025-07-01 | Group 1: $0-10M | 2 Year | 2025
Under Development | ES-106 | N/A | M127 | 115 | Eversource | NH | Degradation of structures. conductor, shield wire and/or hardware | Replace structures. conductor, shield wire and/or hardware |  |  |  |  | 2025-12-01 | Group 2: $10-25M | 2 Year | 2025
Under Development | ES-107 | N/A | 373, 385, 391 | 115 | Eversource | NH | Degradation of structures. conductor, shield wire and/or hardware | Replace structures. conductor, shield wire and/or hardware |  |  |  |  | 2025-06-01 | Group 2: $10-25M | 3-5 Year | 2024 or earlier
Under Development | ES-108 | N/A | 367 | 115 | Eversource | NH | Degradation of structures. conductor, shield wire and/or hardware | Degradation of structures. conductor, shield wire and/or hardware |  |  |  |  | 2026-02-01 | Group 1: $0-10M | 2 Year | 2025
Under Development | ES-109 | N/A | A126 | 115 | Eversource | NH | Degradation of structures. conductor, shield wire and/or hardware | Degradation of structures. conductor, shield wire and/or hardware |  |  |  |  | TBD | Group 1: $0-10M | 2 Year | 2025
Under Development | ES-110 | N/A | Q171 | 115 | Eversource | NH | Degradation of structures. conductor, shield wire and/or hardware | Degradation of structures. conductor, shield wire and/or hardware |  |  |  |  | TBD | Group 1: $0-10M | 2 Year | 2025
Under Development | ES-111 | N/A | 191 | 115 | Eversource | NH | Telecom need | OPGW Instalation |  |  |  |  | TBD | Group 1: $0-10M | 3-5 Year | 2025
Under Development | ES-112 | N/A | E194 | 115 | Eversource | NH | Degradation of structures. conductor, shield wire and/or hardware | Replace structures. conductor, shield wire and/or hardware |  |  |  |  | TBD | Group 1: $0-10M | 3-5 Year | 2025
Under Development | ES-113 | N/A | C129 | 115 | Eversource | NH | Degradation of structures. conductor, shield wire and/or hardware | Replace structures. conductor, shield wire and/or hardware |  |  |  |  | TBD | Group 1: $0-10M | 3-5 Year | 2025
Under Development | ES-114 | N/A | H141 | 115 | Eversource | NH | Degradation of structures. conductor, shield wire and/or hardware | Replace structures. conductor, shield wire and/or hardware |  |  |  |  | TBD | Group 1: $0-10M | 3-5 Year | 2025
Under Development | ES-115 | N/A | A253 | 115 | Eversource | NH | Degradation of structures. conductor, shield wire and/or hardware | Replace structures. conductor, shield wire and/or hardware |  |  |  |  | TBD | Group 1: $0-10M | 3-5 Year | 2025
Under Development | ES-116 | N/A | D121 | 115 | Eversource | NH | Degradation of structures. conductor, shield wire and/or hardware | Replace structures. conductor, shield wire and/or hardware |  |  |  |  | TBD | Group 1: $0-10M | 3-5 Year | 2025
Under Development | NEP-032 | N/A | 314 | 345 | New England Power | MA | Degradation of structures. conductor, shield wire and/or hardware | Replace structures. conductor, shield wire and/or hardware |  |  |  |  | 2026-10-01 | Group 3: $25-100M | 6-10 Year | 2024 or earlier
Under Development | NEP-033 | N/A | E-157/E-157W | 115 | New England Power | MA | Degradation of structures. conductor, shield wire and/or hardware | Replace structures. conductor, shield wire and/or hardware |  |  |  |  | 2026-04-01 | Group 4: $100M+ | 3-5 Year | 2024 or earlier
Under Development | NEP-034 | N/A | 323 | 345 | New England Power | MA | Degradation of structures. conductor, shield wire and/or hardware | Replace structures. conductor, shield wire and/or hardware |  |  |  |  | 2025-10-24 | Group 3: $25-100M | 6-10 Year | 2024 or earlier
Under Development | NEP-035 | N/A | 394/397 | 345 | New England Power | MA | Degradation of structures. conductor, shield wire and/or hardware | Replace structures. conductor, shield wire and/or hardware |  |  |  |  | 2025-10-24 | Group 4: $100M+ | 3-5 Year | 2024 or earlier
Under Development | NEP-036 | N/A | Northboro Rd Substation | 115/69 | New England Power | MA | Aging substation infrastructure, breakers, transformer/autotransformer, relays and/or control house | Control House Rebuild |  |  |  |  | 2025-11-01 | Group 3: $25-100M | 3-5 Year | 2024 or earlier
Under Development | NEP-037 | N/A | I-135S/J-136S | 115 | New England Power | MA | Degradation of structures. conductor, shield wire and/or hardware | Replace structures. conductor, shield wire and/or hardware |  |  |  |  | 2026-01-01 | Group 2: $10-25M | 3-5 Year | 2024 or earlier
Under Development | NEP-038 | N/A | K-137E/L-138E | 115 | New England Power | MA | Degradation of structures. conductor, shield wire and/or hardware | Replace structures. conductor, shield wire and/or hardware |  |  |  |  | 2026-02-01 | Group 4: $100M+ | 3-5 Year | 2024 or earlier
Under Development | NEP-039 | N/A | M-39 | 69 | New England Power | MA | Degradation of structures. conductor, shield wire and/or hardware | Replace structures. conductor, shield wire and/or hardware |  |  |  |  | 2025-12-24 | Group 3: $25-100M | 6-10 Year | 2024 or earlier
Under Development | NEP-040 | N/A | O-15N | 69 | New England Power | MA | Degradation of structures. conductor, shield wire and/or hardware | Replace structures. conductor, shield wire and/or hardware |  |  |  |  | 2025-11-01 | Group 3: $25-100M | 3-5 Year | 2024 or earlier
Under Development | NEP-041 | N/A | S-145E/T-146E | 115 | New England Power | MA | Degradation of structures. conductor, shield wire and/or hardware | Replace structures. conductor, shield wire and/or hardware |  |  |  |  | 2026-01-24 | Group 3: $25-100M | 3-5 Year | 2024 or earlier
Under Development | NEP-042 | N/A | W-23 | 69 | New England Power | MA | Degradation of structures. conductor, shield wire and/or hardware | Replace structures. conductor, shield wire and/or hardware |  |  |  |  | 2026-02-24 | Group 2: $10-25M | 3-5 Year | 2024 or earlier
Under Development | NEP-043 | N/A | Y-177 | 115 | New England Power | MA | Degradation of structures. conductor, shield wire and/or hardware | Replace structures. conductor, shield wire and/or hardware |  |  |  |  | 2026-03-24 | Group 3: $25-100M | 3-5 Year | 2024 or earlier
Under Development | NEP-044 | N/A | 326 | 345 | New England Power | MA | Degradation of structures. conductor, shield wire and/or hardware | Replace structures. conductor, shield wire and/or hardware |  |  |  |  | 2026-01-01 | Group 4: $100M+ | 6-10 Year | 2024 or earlier
Under Development | NEP-045 | N/A | 301 | 345 | New England Power | MA | Degradation of structures. conductor, shield wire and/or hardware | Replace structures. conductor, shield wire and/or hardware |  |  |  |  | 2025-10-24 | Group 4: $100M+ | 3-5 Year | 2024 or earlier
Under Development | NEP-046 | N/A | Q-117 | 115 | New England Power | MA | Degradation of structures. conductor, shield wire and/or hardware | Replace structures. conductor, shield wire and/or hardware |  |  |  |  | 2026-03-01 | Group 3: $25-100M | 3-5 Year | 2024 or earlier
Under Development | NEP-047 | N/A | Otter River Substation | 69 | New England Power | MA | Aging substation infrastructure, breakers, transformer/autotransformer, relays and/or control house | Full substation rebuild |  |  |  |  | 2026-02-01 | Group 3: $25-100M | 6-10 Year | 2024 or earlier
Under Development | NEP-048 | N/A | Palmer #503 Substation | 115/69 | New England Power | MA | Aging substation infrastructure, breakers, transformer/autotransformer, relays and/or control house | Partial rebuild substation |  |  |  |  | TBD | Group 1: $0-10M | 6-10 Year | 2024 or earlier
Under Development | NEP-049 | N/A | U2 | 115 | New England Power | MA | Degradation of structures. conductor, shield wire and/or hardware | Replace structures. conductor, shield wire and/or hardware |  |  |  |  | 2025-12-01 | Group 3: $25-100M | 6-10 Year | 2024 or earlier
Under Development | NEP-073 | N/A | I-135/J-136N | 115 | New England Power | MA | Degradation of structures. conductor, shield wire and/or hardware | Replace structures. conductor, shield wire and/or hardware |  |  |  |  | 2025-10-01 | Group 4: $100M+ | 3-5 Year | 2025
Under Development | RIE-005 | N/A | S171/S171S/T172S | 115 | Rhode Island Energy | RI | Degradation of structures. conductor, shield wire and/or hardware | Replace structures. conductor, shield wire and/or hardware |  |  |  |  | 2025-08-07 | Group 2: $10-25M | 2 Year | 2025
Under Development | RIE-006 | N/A | NERC CIP-014 - Physical Security Upgrades | REDACTED | Rhode Island Energy | RI | CIP-014 Physical Security Upgrades | CIP-014 Physical Security Upgrades |  |  |  |  | TBD | Group 1: $0-10M | 2 Year | 2024 or earlier
Under Development | RIE-007 | N/A | 1870S | 115 | Rhode Island Energy | RI | Aging line and degredation of structures | Replace structures. conductor, shield wire and/or hardware |  |  |  |  | TBD | Group 3: $25-100M | 3-5 Year | 2024 or earlier
Under Development | RIE-008 | N/A | H17 | 115 | Rhode Island Energy | RI | Aging structures. conductor, shield wire and/or hardware | Replace structures. conductor, shield wire and/or hardware |  |  |  |  | TBD | Group 1: $0-10M | 3-5 Year | 2024 or earlier
Under Development | RIE-009 | N/A | 332 | 345 | Rhode Island Energy | RI | Aging line and degredation of structures | Full rebuild or targeted refurbishment |  |  |  |  | TBD | Group 3: $25-100M | 2 Year | 2024 or earlier
Under Development | RIE-010 | N/A | 347 | 345 | Rhode Island Energy | RI | Aging line and degredation of structures | Full rebuild or targeted refurbishment |  |  |  |  | TBD | Group 3: $25-100M | 3-5 Year | 2024 or earlier
Under Development | RIE-011 | N/A | Franklin Square/Manchester St | 115 | Rhode Island Energy | RI | Aging substation infrastructure, breakers, transformer/autotransformer, relays and/or control house | Relay upgrades |  |  |  |  | TBD | Group 3: $25-100M | 3-5 Year | 2024 or earlier
Under Development | RIE-012 | N/A | West Kingston | 115 | Rhode Island Energy | RI | Aging substation infrastructure, breakers, transformer/autotransformer, relays and/or control house | Relay Upgrades / new transmission control cubicle |  |  |  |  | TBD | Group 2: $10-25M | 3-5 Year | 2024 or earlier
Under Development | RIE-013 | N/A | Kenyon | 115 | Rhode Island Energy | RI | Aging substation infrastructure, breakers, transformer/autotransformer, relays and/or control house | Relay Upgrades / new transmission control cubicle |  |  |  |  | TBD | Group 2: $10-25M | 3-5 Year | 2024 or earlier
Under Development | RIE-014 | N/A | Wood River | 115 | Rhode Island Energy | RI | Aging substation infrastructure, breakers, transformer/autotransformer, relays and/or control house | Relay Upgrades / new transmission control cubicle |  |  |  |  | TBD | Group 2: $10-25M | 3-5 Year | 2024 or earlier
Under Development | RIE-015 | N/A | Staples | 115 | Rhode Island Energy | RI | Aging substation infrastructure, breakers, transformer/autotransformer, relays and/or control house | Relay Upgrades / new transmission control cubicle |  |  |  |  | TBD | Group 2: $10-25M | 3-5 Year | 2024 or earlier
Under Development | RIE-016 | N/A | Valley Sub | 115 | Rhode Island Energy | RI | Aging substation infrastructure, breakers, transformer/autotransformer, relays and/or control house | Relay Upgrades / new transmission control cubicle |  |  |  |  | TBD | Group 2: $10-25M | 3-5 Year | 2024 or earlier
Under Evaluation | ES-117 | N/A | 1977 | 115 | Eversource | CT | Degradation of structures. conductor, shield wire and/or hardware | Replace structures. conductor, shield wire and/or hardware |  |  |  |  | TBD | Group 1: $0-10M | 3-5 Year | 2024 or earlier
Under Evaluation | ES-118 | N/A | Haddam Substation | 115 | Eversource | CT | Aging substation infrastructure, breakers, transformer/autotransformer, relays and/or control house | Relay upgrades |  |  |  |  | TBD | TBD | 3-5 Year | 2024 or earlier
Under Evaluation | ES-119 | N/A | 1785 | 115 | Eversource | CT | Degradation of structures. conductor, shield wire and/or hardware | Replace structures. conductor, shield wire and/or hardware |  |  |  |  | TBD | Group 1: $0-10M | 3-5 Year | 2024 or earlier
Under Evaluation | ES-120 | N/A | 1750 | 115 | Eversource | CT | Degradation of structures. conductor, shield wire and/or hardware | Replace structures. conductor, shield wire and/or hardware |  |  |  |  | 2026-09-01 | TBD | TBD | 2024 or earlier
Under Evaluation | ES-121 | N/A | 1768 | 115 | Eversource | CT | Degradation of structures. conductor, shield wire and/or hardware | Replace structures. conductor, shield wire and/or hardware |  |  |  |  | TBD | TBD | TBD | 2025
Under Evaluation | ES-122 | N/A | North Cambridge #509 Substation | 345/115 | Eversource | MA | BPS/DIR4 upgrades, preimary and secondary relay upgrades, control house upgrades, etc. | Review of existing control house and primary and secondary protection schemes |  |  |  |  | TBD | TBD | 3-5 Year | 2024 or earlier
Under Evaluation | ES-123 | N/A | Mashpee STA 946 | 115 | Eversource | MA | Degradation of Mobile Cap Bank | Mobile Cap Bank Replacement |  |  |  |  | TBD | TBD | TBD | 2025
Under Evaluation | ES-124 | N/A | 326 | 115 | Eversource | NH | Degradation of structures. conductor, shield wire and/or hardware | Replace structures. conductor, shield wire and/or hardware |  |  |  |  | TBD | TBD | TBD | 2025
Under Evaluation | NEP-050 | N/A | Z-126/A-127 | 115 | New England Power | MA | Degradation of structures. conductor, shield wire and/or hardware | Replace structures. conductor, shield wire and/or hardware |  |  |  |  | TBD | TBD | TBD | 2024 or earlier
Under Development | NEP-051 | N/A | O-167/P-168 | 115 | New England Power | MA | HPFF UG Cable Replacement | Replace HPFF with solid dielectric cable |  |  |  |  | TBD | TBD | TBD | 2024 or earlier
Under Evaluation | NEP-052 | N/A | E-183/F-184 | 115 | New England Power | MA | Degradation of structures. conductor, shield wire and/or hardware | Replace structures. conductor, shield wire and/or hardware |  |  |  |  | TBD | Group 4: $100M+ | 6-10 Year | 2024 or earlier
Under Evaluation | NEP-053 | N/A | O-215/N-214 | 230 | New England Power | MA | Degradation of structures. conductor, shield wire and/or hardware | Replace structures. conductor, shield wire and/or hardware |  |  |  |  | 2026-06-30 | Group 4: $100M+ | 6-10 Year | 2024 or earlier
Under Evaluation | NEP-054 | N/A | 331 | 345 | New England Power | MA | Degradation of structures. conductor, shield wire and/or hardware | Replace structures. conductor, shield wire and/or hardware |  |  |  |  | 2026-04-24 | Group 4: $100M+ | 6-10 Year | 2024 or earlier
Under Evaluation | NEP-055 | N/A | Gardner Twr Sub Motorized switches | 69 | New England Power | MA | Aging substation infrastructure, breakers, transformer/autotransformer, relays and/or control house | Replace structures. conductor, shield wire and/or hardware |  |  |  |  | TBD | TBD | 6-10 Year | 2024 or earlier
Under Evaluation | NEP-056 | N/A | 356 | 345 | New England Power | MA | Degradation of structures. conductor, shield wire and/or hardware | Replace structures. conductor, shield wire and/or hardware |  |  |  |  | TBD | Group 1: $0-10M | 6-10 Year | 2024 or earlier
Under Evaluation | NEP-057 | N/A | 357 | 345 | New England Power | MA | Degradation of structures. conductor, shield wire and/or hardware | Replace structures. conductor, shield wire and/or hardware |  |  |  |  | TBD | TBD | TBD | 2024 or earlier
Under Evaluation | NEP-058 | N/A | A-127/B-128/Z-126 | 115 | New England Power | MA | Degradation of structures. conductor, shield wire and/or hardware | Replace structures. conductor, shield wire and/or hardware |  |  |  |  | TBD | TBD | TBD | 2024 or earlier
Under Evaluation | NEP-059 | N/A | Read St Substation | 115/69 | New England Power | MA | Aging substation infrastructure, breakers, transformer/autotransformer, relays and/or control house | Full substation rebuild |  |  |  |  | TBD | Group 3: $25-100M | 6-10 Year | 2024 or earlier
Under Evaluation | NEP-060 | N/A | D-130 | 115 | New England Power | MA | Degradation of structures. conductor, shield wire and/or hardware | Replace structures. conductor, shield wire and/or hardware |  |  |  |  | TBD | TBD | TBD | 2024 or earlier
Under Evaluation | NEP-061 | N/A | S1 | 115 | New England Power | MA | Degradation of structures. conductor, shield wire and/or hardware | Replace structures. conductor, shield wire and/or hardware |  |  |  |  | 2025-09-01 | Group 3: $25-100M | 3-5 Year | 2024 or earlier
Under Evaluation | NEP-062 | N/A | M13/L14/N12 | 115 | New England Power | MA | Degradation of structures. conductor, shield wire and/or hardware | Replace structures. conductor, shield wire and/or hardware |  |  |  |  | TBD | Group 3: $25-100M | 6-10 Year | 2024 or earlier
Under Evaluation | NEP-063 | N/A | Pratts Junction Substation | 115 | New England Power | MA | Aging substation infrastructure, breakers, transformer/autotransformer, relays and/or control house | Partial rebuild substation |  |  |  |  | 2027-01-01 | Group 3: $25-100M | 6-10 Year | 2024 or earlier
Under Evaluation | NEP-064 | N/A | Westborough Substation | 69 | New England Power | MA | Aging substation infrastructure, breakers, transformer/autotransformer, relays and/or control house | Partial rebuild substation |  |  |  |  | TBD | TBD | TBD | 2024 or earlier
Under Evaluation | NEP-065 | N/A | B-154N, C-155N, B-154S and C-155S | 115 | New England Power | MA | Degradation of structures. conductor, shield wire and/or hardware | Replace structures. conductor, shield wire and/or hardware |  |  |  |  | 2026-07-24 | Group 4: $100M+ | 6-10 Year | 2024 or earlier
Under Evaluation | NEP-066 | N/A | E1 | 115 | New England Power | MA | Degradation of structures. conductor, shield wire and/or hardware | Replace structures. conductor, shield wire and/or hardware |  |  |  |  | TBD | TBD | TBD | 2024 or earlier
Under Evaluation | NEP-067 | N/A | Ware Substation | 69 | New England Power | MA | Aging substation infrastructure, breakers, transformer/autotransformer, relays and/or control house | Partial rebuild substation |  |  |  |  | 2026-11-01 | Group 2: $10-25M | 6-10 Year | 2024 or earlier
Under Evaluation | NEP-068 | N/A | F-132 | 115 | New England Power | MA | Degradation of structures. conductor, shield wire and/or hardware | Replace structures. conductor, shield wire and/or hardware |  |  |  |  | 2026-12-30 | Group 2: $10-25M | 6-10 Year | 2024 or earlier
Under Evaluation | NEP-069 | N/A | Millbury 5 Indoor GIS | 115/69 | New England Power | MA | Aging substation infrastructure, breakers, transformer/autotransformer, relays and/or control house | Partial rebuild substation |  |  |  |  | 2027-12-30 | Group 3: $25-100M | 6-10 Year | 2024 or earlier
Under Evaluation | NEP-070 | N/A | Robinson Ave | 115/69 | New England Power | MA | Aging substation infrastructure, breakers, transformer/autotransformer, relays and/or control house | Partial rebuild substation |  |  |  |  | TBD | TBD | TBD | 2024 or earlier
Under Evaluation | NEP-071 | N/A | X-176 | 115 | New England Power | MA | Degradation of structures. conductor, shield wire and/or hardware | Replace structures. conductor, shield wire and/or hardware |  |  |  |  | 2026-12-30 | Group 3: $25-100M | 6-10 Year | 2025
Under Evaluation | NEP-072 | N/A | N-40 | 69 | New England Power | MA/VT | Degradation of structures. conductor, shield wire and/or hardware | Replace structures. conductor, shield wire and/or hardware |  |  |  |  | TBD | TBD | TBD | 2024 or earlier
Under Evaluation | RIE-017 | N/A | 1870 | 115 | Rhode Island Energy | RI | Aging structures. conductor, shield wire and/or hardware | Full rebuild or targeted refurbishment |  |  |  |  | TBD | TBD | 3-5 Year | 2024 or earlier
Under Evaluation | RIE-018 | N/A | 1870N | 115 | Rhode Island Energy | RI | Aging structures. conductor, shield wire and/or hardware | Full rebuild or targeted refurbishment |  |  |  |  | TBD | TBD | 3-5 Year | 2024 or earlier
Under Evaluation | RIE-019 | N/A | Q-143 | 115 | Rhode Island Energy | RI | Aging line and degredation of structures | Full rebuild or targeted refurbishment |  |  |  |  | TBD | Group 2: $10-25M | 3-5 Year | 2024 or earlier
Under Evaluation | RIE-020 | N/A | R-144N | 115 | Rhode Island Energy | RI | Aging line and degredation of structures | Full rebuild or targeted refurbishment |  |  |  |  | TBD | Group 2: $10-25M | 3-5 Year | 2024 or earlier
Under Evaluation | RIE-021 | N/A | V-148N | 115 | Rhode Island Energy | RI | Aging structures. conductor, shield wire and/or hardware | Full rebuild or targeted refurbishment |  |  |  |  | TBD | TBD | 6-10 Year | 2024 or earlier
Under Evaluation | RIE-022 | N/A | R9 | 115 | Rhode Island Energy | RI | Aging structures. conductor, shield wire and/or hardware | Full rebuild or targeted refurbishment |  |  |  |  | TBD | TBD | 6-10 Year | 2024 or earlier
Under Evaluation | RIE-023 | N/A | E-105 | 115 | Rhode Island Energy | RI | Aging equipment and equipment failures | Full rebuild or targeted refurbishment |  |  |  |  | TBD | TBD | 3-5 Year | 2024 or earlier
Under Evaluation | RIE-024 | N/A | F-106 | 115 | Rhode Island Energy | RI | Aging equipment and equipment failures | Full rebuild or targeted refurbishment |  |  |  |  | TBD | TBD | 3-5 Year | 2024 or earlier
Under Evaluation | UI-014 | N/A | 8500, 8700, 8702 | 115 | United Illuminating Company | CT | Aging obsolete LPFF UG cables, degredation of ducts and manholes | Replace with XLPE cable in new manhole and duct bank system. |  |  |  |  | 2026-04-26 | Group 4: $100M+ | 6-10 Year | 2024 or earlier
Under Evaluation | UI-015 | N/A | Milvon | 115 | United Illuminating Company | CT | Critical equipment failure due to past flooding events. | Raise critical equipment above 100 year flood elevation. |  |  |  |  | TBD | Group 1: $0-10M | 3-5 Year | 2025
Under Evaluation | VEP-010 | N/A | Granite Sync cond | 115 | Vermont Electric Power Co | VT | Aging controls | Control replacments |  |  |  |  | TBD | Group 1: $0-10M | 2 Year | 2024 or earlier
Under Evaluation | VEP-011 | N/A | Line K51 | 115 | Vermont Electric Power Co | VT | Degradation of structures. conductor, shield wire and/or hardware | Replace structures. conductor, shield wire and/or hardware |  |  |  |  | TBD | Group 2: $10-25M | 2 year | 2024 or earlier
Under Evaluation | VEP-012 | N/A | Essex substation | 115 | Vermont Electric Power Co | VT | Aging substation infrastructure, breakers, transformer/autotransformer, relays and/or control house | Partial rebuild substation |  |  |  |  | TBD | Group 1: $0-10M | 6-10 Year | 2024 or earlier
Under Evaluation | VEP-013 | N/A | Vermont Yankee substation | 115 | Vermont Electric Power Co | VT | Aging substation infrastructure, breakers, transformer/autotransformer, relays and/or control house | Partial rebuild substation |  |  |  |  | TBD | Group 2: $10-25M | 3-5 year | 2024 or earlier
Under Evaluation | VEP-014 | N/A | Line K54 | 115 | Vermont Electric Power Co | VT | Degradation of structures. conductor, shield wire and/or hardware | Complete line rebuild |  |  |  |  | TBD | Group 3: $25-100M | 3-5 year | 2024 or earlier
Under Evaluation | VEP-015 | N/A | Line F206 | 230 | Vermont Electric Power Co | VT | Degradation of structures. conductor, shield wire and/or hardware | Complete line rebuild |  |  |  |  | TBD | Group 3: $25-100M | 3-5 Year | 2024 or earlier
Under Evaluation | VEP-016 | N/A | Coolidge transformer and substation | 345/115 | Vermont Electric Power Co | VT | Aging substation infrastructure, breakers, transformer/autotransformer, relays and/or control house | Partial rebuild substation |  |  |  |  | TBD | Group 2: $10-25M | 3-5 Year | 2024 or earlier
Under Evaluation | VEP-017 | N/A | Highgate Converter | 115 | Vermont Electric Power Co | VT | Aging substation infrastructure, breakers, transformer/autotransformer, relays and/or control house | Relocate substation |  |  |  |  | TBD | Group 4: $100M+ | 6-10 Year | 2024 or earlier
Under Evaluation | VEP-018 | N/A | Cold River | 115 | Vermont Electric Power Co | VT | Aging substation infrastructure, breakers, transformer/autotransformer, relays and/or control house | Partial rebuild substation |  |  |  |  | TBD | Group 2: $10-25M | 6-10 Year | 2024 or earlier
Under Evaluation | VEP-019 | N/A | West Rutland | 345/115 | Vermont Electric Power Co | VT | Aging substation infrastructure, breakers, transformer/autotransformer, relays and/or control house | Partial rebuild substation |  |  |  |  | TBD | Group 2: $10-25M | 6-10 Year | 2025
Under Evaluation | VEP-020 | N/A | Granite | 230/115 | Vermont Electric Power Co | VT | Aging substation infrastructure, breakers, transformer/autotransformer, relays and/or control house | Partial rebuild substation |  |  |  |  | TBD | Group 1: $0-10M | 6-10 Year | 2025
Under Evaluation | VEP-021 | N/A | S. Hero | 115 | Vermont Electric Power Co | VT | Aging substation infrastructure, breakers, transformer/autotransformer, relays and/or control house | Partial rebuild substation |  |  |  |  | TBD | Group 1: $0-10M | 3-5 Year | 2025
Under Evaluation | VEP-022 | N/A | Line K28 | 115 | Vermont Electric Power Co | VT | Degradation of structures. conductor, shield wire and/or hardware | Replace structures. conductor, shield wire and/or hardware |  |  |  |  | TBD | Group 2: $10-25M | 3-5 Year | 2025
Under Evaluation | VEP-023 | N/A | Line K30 | 115 | Vermont Electric Power Co | VT | Degradation of structures. conductor, shield wire and/or hardware | Replace structures. conductor, shield wire and/or hardware |  |  |  |  | TBD | Group 2: $10-25M | 3-5 Year | 2025
Under Evaluation | VEP-024 | N/A | Line K39 | 115 | Vermont Electric Power Co | VT | Degradation of structures. conductor, shield wire and/or hardware | Replace structures. conductor, shield wire and/or hardware |  |  |  |  | TBD | Group 2: $10-25M | 3-5 Year | 2025
Under Evaluation | VEP-025 | N/A | Line K47 | 115 | Vermont Electric Power Co | VT | Degradation of structures. conductor, shield wire and/or hardware | Replace structures. conductor, shield wire and/or hardware |  |  |  |  | TBD | Group 2: $10-25M | 3-5 Year | 2025
Under Evaluation | VEP-026 | N/A | Line K60 | 115 | Vermont Electric Power Co | VT | Degradation of structures. conductor, shield wire and/or hardware | Replace structures. conductor, shield wire and/or hardware |  |  |  |  | TBD | Group 2: $10-25M | 3-5 Year | 2025
Under Evaluation | VEP-027 | N/A | Line K80 | 115 | Vermont Electric Power Co | VT | Degradation of structures. conductor, shield wire and/or hardware | Replace structures. conductor, shield wire and/or hardware |  |  |  |  | TBD | Group 2: $10-25M | 3-5 Year | 2025

## Contact Info and Data Fields
For questions please contact the individuals below
| Company | Name | Email
| Avangrid (CMP and MEPCO) | Devin Carrier | devin.carrier@cmpco.com
| Avangrid (UI) | Joshua Cefaratti | joshua.cefaratti@cmpco.com
| Eversource | Dave Burnham | david.burnham@eversource.com
| National Grid | Rafael Panos | rafael.panos@nationalgrid.com
| Rhode Island Energy | Kyra Lagunilla | KLagunilla@pplweb.com
| VELCO | Frank Ettori | fettori@velco.com
| Versant* | Dave Norman | david.norman@versantpower.com
*Note: there are no current or forecasted projects by Versant that meet the conditions for inclusion
Data Field Descriptions
Project Stage
Under Evaluation
Facility is currently being evaluated for possible asset condition project, but no formal scope/cost estimates have been developed
Under Development
Project planning is underway; project scope and conceptual cost estimates are currently being developed
Presented to PAC
Presented to PAC – Project has been presented to PAC and is listed on most recent Asset Condition List
AC Forecast ID Number
Unique ID added in 2025. Note this number is only for this exhibit and is not related to Any other ID numbers for other purposes such as PPA or TCA numbers.
Asset Condition List (ACL) ID
ACL ID is provided for projects already listed on the ISO NE Asset Condition list as of June 2025
https://www.iso-ne.com/static-assets/documents/100025/final_asset_condition_list_june2025.xlsx
Line Number or Station Name/Number
Voltage level for lines or high/low voltage for stations
Primary Equipment Owner
State
| Current Asset Condition | Brief description of condition requiring action or attention
| Anticipated solution | Most likely solution based on the TO’s current assessment
May become proposed solution presented to PAC or be modified as additional analysis is completed
| Year Added | Year added to this file
For projects listed as “Presented to PAC”, the following information is available:
PAC Presentation Date
Status on Asset Condition List (Concept, Proposed, Planned, Under Construction)
Estimated Cost ($)
Estimated In Service Date (ISD), Year
For projects listed as “Under Development”, the following information is available:
Anticipated PAC Presentation date, Month & Year
Anticipated Cost Category
$0-10M
$10-25M
$25-100M
$100M+
Planning Horizon (anticipated in-service dates)
1 Year
2 Year
3-5 Year
6-10 Year : TOs have focused on projects expected within the next 5 years, but included information on projects anticipated within the 6 - 10 year timeframe where available
For projects listed as “Under Evaluation”, the information above is provided where available

## Tables
New England Asset Owners 2025 Asset Condition Project Foreast
August 2025
Table 1 of 3: Project Stage Reconciliation 2024 - 2025
| Primary Equipment Owner | Project Stage | 2024 | Removed - placed in service | Removed - other reasons | Moved to "Under Evaluation" | Moved to "Under Development" | Moved to "Presented to PAC" | New Additions | 2025
| CMP/MEPCO | Presented to PAC | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1
| CMP/MEPCO | Under Development | 5 | 0 | 0 | 0 | 0 | 0 | 5 | 10
| CMP/MEPCO | Under Evaluation | 1 | 0 | -1 | 0 | 0 | 0 | 0 | 0
| Eversource | Presented to PAC | 64 | -30 | 0 | 0 | 0 | 16 | 7 | 57
| Eversource | Under Development | 42 | 0 | -2 | 0 | 11 | -11 | 19 | 59
| Eversource | Under Evaluation | 24 | 0 | -3 | 0 | -11 | -5 | 3 | 8
| New England Power | Presented to PAC | 25 | -5 | 0 | 0 | 0 | 9 | 2 | 31
| New England Power | Under Development | 30 | 0 | -2 | -1 | 0 | -8 | 1 | 20
| New England Power | Under Evaluation | 21 | 0 | 0 | 1 | 0 | -1 | 1 | 22
| Rhode Island Energy | Presented to PAC | 6 | -2 | 0 | 0 | 0 | 0 | 0 | 4
| Rhode Island Energy | Under Development | 3 | 0 | 0 | 0 | 8 | 0 | 1 | 12
| Rhode Island Energy | Under Evaluation | 16 | 0 | 0 | 0 | -8 | 0 | 0 | 8
| United Illuminating Company | Presented to PAC | 17 | -4 | 0 | 0 | 0 | 0 | 0 | 13
| United Illuminating Company | Under Development | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| United Illuminating Company | Under Evaluation | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 2
| Vermont Electric Power Co | Presented to PAC | 10 | -2 | 0 | 0 | 0 | 1 | 0 | 9
| Vermont Electric Power Co | Under Development | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Vermont Electric Power Co | Under Evaluation | 10 | 0 | 0 | 0 | 0 | -1 | 9 | 18
| Versant | Presented to PAC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Versant | Under Development | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Versant | Under Evaluation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total | Presented to PAC | 123 | -43 | 0 | 0 | 0 | 26 | 9 | 115
| Total | Under Development | 80 | 0 | -4 | -1 | 19 | -19 | 26 | 101
| Total | Under Evaluation | 73 | 0 | -4 | 1 | -19 | -7 | 14 | 58
| Grand Total |  | 276 | -43 | -8 | 0 | 0 | 0 | 49 | 274
Table 2 of 3: Estimated Cost Comparison of Projects Presented to PAC 2024 - 2025
| Presented to PAC Projects Estimated Cost ($M) |  | 2024 | 2025
| Total |  | 6182.6676 | 5518.9422
Table 3 of 3: Cost Category Comparison 2024 - 2025
| Cost Categories |  | 2024 | 2025
Under Development
|  | Group 1: $0-10M | 11 | 32
|  | Group 2: $10-25M | 20 | 30
|  | Group 3: $25-100M | 20 | 29
|  | Group 4: $100M+ | 8 | 7
|  | TBD | 21 | 3
|  | Total | 80 | 101
Under Evaluation
|  | Group 1: $0-10M | 8 | 8
|  | Group 2: $10-25M | 10 | 15
|  | Group 3: $25-100M | 13 | 8
|  | Group 4: $100M+ | 5 | 6
|  | TBD | 37 | 21
|  | Total | 73 | 58