## Currently Certified Projects
Forward Capacity Auction New Transmission Project Tracker for the Capacity Commitment Period beginning June 1, 2016 through May 31, 2017
State | Projected In Service Date (RSP Date) | Major Project | Project Component | RSP Project Number | I.3.9 Approval | TCA Approval | Responsible TO | FCM Certified In Service Date
CT | 2013-12-01 | NEEWS (Greater Springfield Reliability Project) | North Bloomfield 2A Substation Expansion - add a second 345/115-kV autotransformer | 816 | 2008-09-24 | No | NU | 2013-12-01
CT | 2013-05-01 |  | East Shore 115 kV Oil Circuit Breaker & Disconnect Replacements. | 974 | NR | No | UI | 2011-06-01
CT | 2012-05-01 |  | Grand Avenue 115 kV Switching Station Rebuild. | 976 | 1/7/2009 & 11/22/2010 | No | UI | 2012-05-01
CT | 2013-12-01 | NEEWS (Ancillary Greater Springfield Reliability Project) | Build a new 345 kV line from Manchester to Meekville Junction and re-terminate the 395 line at Meekville Junction | 1054 | 2008-09-24 | No | NU | 2013-07-01
CT | 2011-12-01 | LSP - Sherwood Substation | Sherwood Substation - add a 115/13.8-kV substation with two transformers and a 115-kV circuit breaker. | 1056 | 2008-12-12 | 2011-04-14 | NU | 2012-06-01
CT | 2013-12-01 | Millstone 345kV Circuit Separation project & SLOD SPS System Retirement | Separate the 345kV Double Circuit Tower 310/348 and 371/383 Tower configuration | 1218 | 2010-11-02 | No | NU | 2013-05-01
CT | 2012 | LSP - Stamford Area | Add 4th transformer and build a five breaker ring bus at South End Substation | 1227 | 2011-06-09 | No | NU | 2012-05-01
CT | TBD | LSP - Greater Hartford Area | 115kV breaker addition at Northeast Simsbury Substation | 1230 | 2011-03-30 | No | NU | 2013-12-01
CT | 2015-12-01 | NEEWS (Ancillary Interstate Reliability Project) | Sag elimination on 1410 Line (Montville-Buddington) | 1235 | 2011-06-09 | No | NU | 2012-12-01
MA | 2012-12-01 | Auburn Reliability Transmission System Upgrades | G18, F19 line terminals 115kV upgrades at Bridgewater sub | 59 | 2008-01-28 | No | NGRID | 2012-12-01
MA | 2013-12-01 | NEEWS (Greater Springfield Reliability Project) | Build new 345kV line (3216), Agawam (MA) - North Bloomfield (CT) | 196 | 2008-09-24 | No | NU | 2013-12-01
MA | 2013-12-01 | NEEWS (Greater Springfield Reliability Project) | Rebuild Cadwell to Orchard (1426) 115kV line | 259 | 2008-09-24 | No | NU | 2013-12-01
MA | 2011-12-01 | Greater Boston - Central | Reconductor 115-kV circuits 320-507 and 320-508. (Lexington - Waltham) | 301 | 2011-02-15 | No | NSTAR | 2011-12-01
MA | 2012-12-01 | Worcestor Area Reinforcements | Add new 115kV bay to separate the M-165 & E-157 terminal at Millbury #2 Substation | 673 | 2009-02-27 | No | NGRID | 2012-12-01
MA | 2012-12-01 | Worcestor Area Reinforcements | New Bloomingdale to Vernon Hill 115 kV (UG Cable-3.6 mi.) new 115kV breaker at Bloomingdale & Vernon Hill | 676 | 2009-02-27 | No | NGRID | 2012-12-01
MA | 2013-12-01 | NEEWS (Greater Springfield Reliability Project) | Fairmont 16H Substation Expansion | 687 | 2008-09-24 | No | NU | 2013-12-01
MA | 2013-12-01 | NEEWS (Greater Springfield Reliability Project) | Rebuild Ludlow to Cadwell (1481) 115kV line | 688 | 2008-09-24 | No | NU | 2013-12-01
MA | 2011-05-01 | Greater Rhode Island Transmission Reinforcements | Terminal upgrades at Drumrock, Chartley Pond and Brayton Point | 786 | 2008-04-25 | No | NGRID | 2012-12-01
MA | 2011-12-01 | Greater Rhode Island Transmission Reinforcements (Advanced NEEWS) | Berry Street 345/115 kV substation. | 790 | 04/25/2008 | No | NGRID | 2011-12-01
MA | 2013-12-01 | NEEWS (Greater Springfield Reliability Project) | Reconstruct a new 115kV line South Agawam to Southwick (1768) | 818 | 2008-09-24 | No | NU | 2013-12-01
MA | 2013-12-01 | NEEWS (Greater Springfield Reliability Project) | Build new 345kV line Ludlow - Agawam (3196) | 819 | 2008-09-24 | No | NU | 2013-12-01
MA | 2013-12-01 | NEEWS (Greater Springfield Reliability Project) | Expansion of Agawam 16C 115 kV Substation to include new 345 kV station with two 345/115-kV autotransformers. | 820 | 2008-09-24 | No | NU | 2013-12-01
MA | 2013-12-01 | NEEWS (Greater Springfield Reliability Project) | Ludlow 19S 345 kV Substation Expansion, two 345/115kV Autotransformers replacements. Add two 345kV 120 MVAR Capacitor additions | 823 | 2008-09-24 | No | NU | 2013-12-01
MA | 2013-12-01 | NEEWS (Greater Springfield Reliability Project) | South Agawam 42E Substation Reconfigure | 826 | 2008-09-24 | No | NU | 2013-12-01
MA | 2013-12-01 | NEEWS (Greater Springfield Reliability Project) | Breckwood 115kV circuit 1322 Reactor Bypass and Open Breckwook Substation 1T breaker and maintain breaker in the normally open position | 828 | 2008-09-24 | No | NU | 2013-12-01
MA | 2013-12-01 | NEEWS (Greater Springfield Reliability Project) | Rebuild Agawam to Piper (1230) 115 kV line. | 829 | 2008-09-24 | No | NU | 2013-12-01
MA | 2013-06-01 | Auburn Area Transmission System Upgrades | Expand Auburn St Substation to include 2nd 345/115 kV autotransformer and 345 kV ring bus. | 887 | 2010-02-10 | No | NGRID | 2013-06-01
MA | 2014-04-01 | Auburn Area Transmission System Upgrades | Dupont substation - Upgrade Buswork and convert to BPS substation | 919 | 2010-02-10 | No | NGRID | 2014-04-01
MA | 2012-12-01 | Auburn Area Transmission System Upgrades | Bridgewater substation - Upgrade Buswork and convert to BPS substation | 921 | 2008-01-28 | No | NGRID | 2012-12-01
MA | 2012-11-01 | Central/Western Massachusetts Upgrades | Pratts Jct. - supply 13 kV from T3 and T4. | 925 | 12/17/2007 | No | NGRID | 2013-03-01
MA | 2012-11-01 | Central/Western Massachusetts Upgrades | Pratts Jct. - replace T8 autotransformer with 230 kV 333 mVA, upgrade breaker and bus to 115 kV. Install high side 230 kV breaker. | 926 | 12/17/2007 | No | NGRID | 2013-03-01
MA | 2013-06-01 | Central/Western Massachusetts Upgrades | Millbury -upgrade terminal equipment for O-141, P-142, B-128, A-127 circuit breakers. | 928 | 12/17/2007 | No | NGRID | 2013-06-01
MA | 2013-09-01 | Central/Western Massachusetts Upgrades | Searsburg - install in-line 69 kV breaker for operational flexibility. | 929 | 12/17/2007 | No | NGRID | 2013-09-01
MA | 2012-11-01 | Central/Western Massachusetts Upgrades | Pratts Jct. - increase thermal rating of I-135 and J-136 buswork. | 932 | 12/17/2007 | No | NGRID | 2012-11-01
MA | 2012-12-01 | Central/Western Massachusetts Upgrades | Reconductor #2 Tap from Tower 510 - Webster St. 115 kV circuit. | 934 | 12/17/2007 | No | NGRID | 2013-12-01
MA | 2012-12-01 | Central/Western Massachusetts Upgrades | Reconductor from (A-127E/B-128E) Millbury - Tower 510 115 kV line. | 935 | 12/17/2007 | No | NGRID | 2013-12-01
MA | 2015-12-01 | Central/Western Massachusetts Upgrades | Bear Swamp - install one 230-115 kV 333 mVA auto, one 115 kV breaker and upgrade various terminal equipment. | 937 | 12/17/2007 | No | NGRID | 2015-12-01
MA | 2013-05-01 | Central/Western Massachusetts Upgrades | Deerfield - install a new 115/69KV autotransformer and a 69kV breaker and disconnect switches. | 938 | 12/17/2007 | No | NGRID | 2013-05-01
MA | 2014-06-01 | Central/Western Massachusetts Upgrades | Reconductor sections of A127W line w/795 ACSS (A127 West reconductoring. Tower 510 to Paxton, French King to French King). | 940 | 12/17/2007 | No | NGRID | 2014-06-01
MA | 2013-08-01 | Central/Western Massachusetts Upgrades | Install new Z126 Millbury - Tower #510 115 kV line. | 941 | 12/17/2007 | No | NGRID | 2013-08-01
MA | 2012-12-01 | Central/Western Massachusetts Upgrades | Webster St. - add two 115 kV circuit breakers, | 942 | 12/17/2007 | No | NGRID | 2013-06-01
MA | 2012-12-01 | Central/Western Massachusetts Upgrades | Millbury - new 115 kV breaker position for new line to Twr 510. | 943 | 12/17/2007 | No | NGRID | 2012-12-01
MA | 2014-05-01 | Central/Western Massachusetts Upgrades | Adams - install two new 115 kV breakers and replace two existing 115kV breakers | 945 | 12/17/2007 | No | NGRID | 2014-05-01
MA | 2015-04-01 | Central/Western Massachusetts Upgrades | Convert 69 kV (O-15S) Palmer- Hampden to 115 kV. | 946 | 2011-03-29 | No | NGRID | 2016-06-01
MA | 2014-05-01 | Central/Western Massachusetts Upgrades | Hampden - build new 115 kV substation at 1515/O-15S intersection (4 breaker ring). | 948 | 2011-03-29 | No | NGRID | 2014-10-01
MA | 2011-10-01 | Greater Boston - North | Add a new 115kV 36.7 MVAR capacitor bank at Chelsea. | 969 | 2011-03-20 | NR | NSTAR | 2011-12-01
MA | 2013-12-01 | NEEWS (Greater Springfield Reliability Project) | Build 115-kV Cadwell switching 50F station. | 1010 | 2008-09-24 | No | NU | 2013-12-01
MA | 2013-12-01 | NEEWS (Greater Springfield Reliability Project) | Rebuild Agawam to South Agawam (1781) 115kV line and add a 2nd High Speed Protection | 1070 | 2008-09-24 | No | NU | 2013-12-01
MA | 2013-12-01 | NEEWS (Greater Springfield Reliability Project) | Rebuild Agawam to South Agawam (1782) 115kV line and add a 2nd High Speed Protection | 1071 | 2008-09-24 | No | NU | 2013-12-01
MA | 2013-12-01 | NEEWS (Greater Springfield Reliability Project) | Rebuild Ludlow to Shawinigan (1845) 115kV line and add 2nd High Speed Protection | 1072 | 2008-09-24 | No | NU | 2013-12-01
MA | 2013-12-01 | NEEWS (Greater Springfield Reliability Project) | Reterminate Cadwell to East Springfield (5001) 115kV line | 1073 | 2008-09-24 | No | NU | 2013-12-01
MA | 2013-12-01 | NEEWS (Greater Springfield Reliability Project) | Reterminate Cadwell to East Springfield (5002) 115kV line | 1074 | 2008-09-24 | No | NU | 2013-12-01
MA | 2013-12-01 | NEEWS (Greater Springfield Reliability Project) | Add 2nd high speed protection scheme to Agawam to Elm (1007) 115kV line if the Russell Biomass Plant, queue position #135 is constructed | 1075 | 2008-09-24 | No | NU | 2013-12-01
MA | 2011-12-01 | Agawam-West Springfield Project | Add a 2nd high speed protection scheme to Agawam to West Springfield (1311) 115kV line | 1076 | 2008-09-24 | No | NU | 2013-12-01
MA | 2013-12-01 | NEEWS (Greater Springfield Reliability Project) | Add a 2nd high speed protection scheme to Fairmont to Pineshed (1327) 115kV line | 1078 | 2008-09-24 | No | NU | 2013-12-01
MA | 2013-12-01 | NEEWS (Greater Springfield Reliability Project) | Add a 2nd high speed protection scheme to Fairmont to Mt. Tom (1428) 115kV line | 1079 | 2008-09-24 | No | NU | 2013-12-01
MA | 2013-12-01 | NEEWS (Greater Springfield Reliability Project) | Replace 4T and 6T 115kV circuit breaker to Shawinigan substation | 1080 | 2008-09-24 | No | NU | 2013-12-01
MA | 2011-12-01 | Greater Rhode Island Transmission Reinforcements (Advanced NEEWS) | 345/115kV line interconnections at Berry Street | 1098 | 2008-04-25 | No | NGRID | 2011-12-01
MA | 2013-12-01 | NEEWS (Greater Springfield Reliability Project) | Rebuild Agawam to Chicopee (1314) 115kV line | 1100 | 2008-09-24 | No | NU | 2013-12-01
MA | 2013-12-01 | NEEWS (Greater Springfield Reliability Project) | Rebuild Ludlow to Orchard (1552) 115kV line | 1101 | 2008-09-24 | No | NU | 2013-12-01
MA | 2013-12-01 | NEEWS (Greater Springfield Reliability Project) | Rebuild Fairmont to Piper (1601) 115kV line | 1102 | 2008-09-24 | No | NU | 2013-12-01
MA | 2013-12-01 | NEEWS (Greater Springfield Reliability Project) | Rebuild Fairmont to Chicopee (1602) 115kV line | 1103 | 2008-09-24 | No | NU | 2013-12-01
MA | 2013-12-01 | NEEWS (Greater Springfield Reliability Project) | Rebuild Fairmont to Cadwell (1603) 115kV line and add 2nd High Speed Protection | 1104 | 2008-09-24 | No | NU | 2013-12-01
MA | 2013-12-01 | NEEWS (Greater Springfield Reliability Project) | Rebuild Fairmont to Shawinigan (1604) 115kV line and add a 2nd High Speed Protection | 1105 | 2008-09-24 | No | NU | 2013-12-01
MA | 2011-12-01 | Mystic Breaker Additions Project | Move Transformer 110B Connection at Mystic | 1165 | 2008-03-10 | NR | NSTAR | 2012-05-01
MA | 2013-12-01 | Greater Boston - South | Upgrade the 115kV line 201-501 (Medway-Depot St.) and the 201-502 (Beaver Pond - Depot Street Tap) to a higher capacity line | 1175 | No | NR | NSTAR | 2012-11-01
MA | 2012-12-01 | Greater Boston - North | 128-518 Line Upgrade | 1201 | 2011-03-25 | NR | NSTAR | 2011-12-01
MA | 2013-06-01 | NEEWS (Interstate Reliability Project) | Rebuild 1.2 mile length of line 336 with 2-900 ACSS conductor and replace 5, 345kV 2000 amp disconnect switches with 3000 amp switches at W. Medway station | 1202 | 2011-03-30 | NR | NSTAR | 2013-06-01
MA | 2013-06-01 | Flagg Pond Upgrades | At Flagg Pond Substation upgrade terminal equipment on the I-135N, I-135S, J-136N and J-136S 115kV lines and Zone 3 relay upgrades for the J-136N 115kV line. | 1256 | NR | NR | UNITIL | 2012-06-01
MA | 2014-06-01 | Salem Harbor Retirement | 115kV line Reconductoring of the S-145/T-146 from Tewksbury-North Reading Tap (9.3 miles each) | 1257 | 2011-07-28 | No | NGRID | 2014-05-31
MA | 2014-06-01 | Salem Harbor Retirement | 115kV line Reconductoring of the Y-151 from Tewksbury Junction - West Methuen (8.2) | 1258 | 2011-07-28 | No | NGRID | 2014-05-31
MA | 2014-06-01 | Salem Harbor Retirement | 115kV line Reconductoring of the B154/C-155N from King St Tap - South Danvers (14.5 each way) | 1259 | 2011-07-28 | No | NGRID | 2014-05-31
ME | 2012-12-01 | Down East Reliability Improvement | Contruct 115 kV from Trenton tap (part of Hancock Reliability Project) to new Tunk Lake Substation (2 new breakers) to Harrington Substation to Epping Substation (3 new breakers) | 143 | 05/10/2006 | 2008-06-13 | BHE | 2012-12-01
ME | 2012-06-01 | CMP LSP - Saco Bay Area Reinforcement Project | Establish a new Vallee Lane 115/34.5 kV substation and 115 kV line from Louden S/S to Vallee Lane Substation. | 148 | No | NR | CMP | 2012-12-01
ME | 2014-08-01 | Maine Power Reliability Program (MPRP) | New 345kV Line Construction (Orrington-Albion Rd-Coopers Mills, Coopers Mills-Larrabee Road, Larrabee Road-Suroweic). | 905 | 7/31/2008 & 2/26/09 & 11/22/10 | 2010-01-29 | CMP | 2014-07-01
ME | 2014-05-01 | Maine Power Reliability Program (MPRP) | New 115kV line construction (Orrington-Coopers Mills, Larrabee Road-Middle St,Middle St -Lewiston Lower, Larrabee Road-Livermore Falls, Livermore Falls-Rumford IP) | 906 | 7/31/2008 & 2/26/09 & 11/22/10 | 2010-01-29 | CMP | 2014-07-01
ME | 2014-05-01 | Maine Power Reliability Program (MPRP) | Rebuild Existing 115kV lines: Sections 86 (Bucksport-Belfast), Section 203 (Detroit-Orrington), Sections 60 & 212 (Coopers Mills-Bowman St-Larrabee Road), Sections 89 & 229 (Livermore Falls-Riley-Rumford IP) | 907 | 7/31/2008 & 2/26/09 & 11/22/10 | 2010-01-29 | CMP | 2014-04-01
ME | 2014-07-01 | Maine Power Reliability Program (MPRP) | New 345/115kV Autotransformers (Albion Road, Larrabee Road); Coopers Mills autotransforme replaces Maxcy's autotransformer | 908 | 7/31/2008 & 2/26/09 & 11/22/10 | 2010-01-29 | CMP | 2014-06-01
ME | 2014-08-01 | Maine Power Reliability Program (MPRP) | Add 2-115kV breakers & rebuild 86A, new .25 mile transmission at Belfast forming Sections 86 & 266 | 909 | 7/31/2008 & 2/26/09 & 11/22/10 | 2010-01-29 | CMP | 2014-07-01
ME | 2014-05-01 | Maine Power Reliability Program (MPRP) | Separation of Double Circuit Towers (345kV Kennebec River Crossing 375/377, 115kV Bucksport 65/205) | 1025 | 7/31/2008 & 2/26/09 & 11/22/10 | 2010-01-29 | CMP | 2015-05-01
ME | 2013-12-01 | Maine Power Reliability Program (MPRP) | New 345kV Line Construction associated with (Surowiec-Raven Farm, South Gorham-Maguire Road, Maguire Road-Elliot Switching Station) line work | 1026 | 7/31/2008 & 2/26/09 & 11/22/10 | 1/29/2010 (CMP) 4/14/2011 (NU) | CMP/NU | 2013-12-01
ME | 2013-12-01 | Maine Power Reliability Program (MPRP) | Rebuild existing 115kV Line (Section 250, Maguire Rd-Three Rivers) | 1028 | 7/31/2008 & 2/26/09 & 11/22/10 | 1/29/2010 (CMP) 4/14/2011 (NU) | CMP/NU | 2013-11-01
ME | 2013-11-01 | Maine Power Reliability Program (MPRP) | New 345/115kV Autotransformers (Maguire Road) | 1030 | 7/31/2008 & 2/26/09 & 11/22/10 | 2010-01-29 | CMP | 2013-11-01
ME | 2013-12-01 | Maine Power Reliability Program (MPRP) | Rebel Hill Switching Station | 1031 | 2010-10-22 | No | BHE | 2013-12-01
ME | 2011-12-01 | Maine Power Reliability Program (MPRP) | L 64 Rebuild | 1116 | 2010-10-22 | 2011-06-16 | BHE | 2011-12-01
ME | 2012-05-01 | Heywood Road Project | New 115kV line between Wyman Hydro and Heywood Rd. parallel to exiting Section 83. Install a 115kV circuit breaker at Wyman Hydro termination | 1129 | 2009-01-26 | 2010-12-28 | CMP | 2012-05-01
ME | 2011-11-01 | CMP-LSP Bowman St. Substation | Add 115/34kV transformer | 1131 | 2010-11-22 | NR | CMP | 2011-12-01
ME | 2012-02-01 | CMP-Athens Substation LSP | Add two 115kV circuit breakers on Section 66; and 115/12kV transformer | 1135 | 2007-12-21 | NR | CMP | 2011-12-01
ME | 2013-12-01 | Maine Power Reliability Program (MPRP) | Rerate Line 66 | 1154 | 2010-10-22 | No | BHE | 2013-12-01
ME | 2014-12-01 | Maine Power Reliability Program (MPRP) | Capacitor Bank Addition (10 MVAr at Trenton 34.5kV and Epping) | 1155 | 2010-10-22 | No | BHE | 2013-12-01
ME | 2011-12-01 | Maine Power Reliability Program (MPRP) | Orrington Shunt Cap Reconfiguration | 1156 | 2010-10-22 | 2011-06-16 | BHE | 2012-12-01
ME | 2014-07-01 | Maine Power Reliability Program (MPRP) | Two 40 MVAR reactors at Albion Road, two 40 MVAR reactors at Larabee Road, two 40 MVAR at Coopers Mills | 1158 | 7/31/2008 & 2/26/09 & 11/22/10 | 2010-01-29 | CMP | 2013-12-01
ME | 2012-05-01 | Starks Switching Station | Add 4-115kV circuit breakers in a breaker-and a-half configuration on Section 63 and 2-18 MVAr cap banks at a new Starks Switching Station | 1184 | 2010-09-20 | 2011-03-25 | CMP | 2012-06-01
ME | 2012-12-01 | Lakewood Substation Expansion | Sectionalize Section 241 by adding four 115kV circuit breakers at Lakewood Substation and install a second 115/34.5 kV transformer | 1251 | 2011-04-21 | No | CMP | 2013-11-01
NH | 2011-11-01 | 2nd Deerfield 345/115kV Autotransformer Project | Add 2nd 345/115 kV autotransformer and 3-345kV breakers at Deerfield substation. | 277 | 2009-06-29 | 2011-07-15 | NU | 2012-04-01
NH | 2013-12-01 |  | Replace Comerford 230 kV breakers and add (1) 230 kV bus tie breaker. | 674 | 04/01/2008 | No | NGRID | 2013-12-01
NH | 2013-06-01 |  | Rebuild Bellows Falls Substation and install 115 kV capacitor bank. | 680 | 01/28/2008 | No | NGRID | 2013-06-01
NH | 2011-10-01 | 2nd Deerfield 345/115kV Autotransformer Project | Reconductor 115kV C129 Line | 1140 | 2009-06-29 | 2011-07-15 | NU | 2013-12-01
NH | 2012-06-01 | LSP New Eagle Substation and 115/34.5KV transformer | New 115kV Eagle Substation connected to 115/34.5kV Thornton Substation | 1182 | 2010-07-27 | No | NU | 2012-06-01
NH | 2011-12-01 |  | Install 115kV two 13.3 MVAR capacitor banks at Oak Hill substation | 1219 | 2011-02-28 | NR | NU | 2011-12-01
RI | 2013-04-01 | NEEWS (Rhode Island Reliability Project) | New Kent County to West Farnum 345kV (359) line. | 795 | 2008-09-24 | No | NGRID | 2014-03-01
RI | 2011-12-01 | NEEWS (Rhode Island Reliability Project) | Upgrade of 115kV terminal equipment at Franklin Square. | 798 | 2008-09-24 | No | NGRID | 2012-06-01
RI | 2012-12-01 | NEEWS (Interstate Reliability Project) | Upgrade and expand the 345kV West Farnum Substation Equipment | 1095 | 2008-09-24 | No | NGRID | 2013-12-01
RI | 2012-06-01 | NEEWS (Rhode Island Reliability Project) | Drumrock substation: Terminal equipment upgrades, Protection modifications and upgrades to meet BPS standards | 1096 | 2008-09-24 | No | NGRID | 2012-12-01
RI | 2013-01-01 | NEEWS (Rhode Island Reliability Project) | Relocate and Rebuild 115kV lines in the same ROW associated with new 345kV line from W. Farnum to Kent County including S-175, T172N and T-172S with associated terminal equipment upgrade. | 1097 | 2008-09-24 | No | NGRID | 2013-12-01
RI | 2012-06-01 | NEEWS (Rhode Island Reliability Project) | Hartford Ave 115kV terminal equipment upgrades | 1099 | 2008-09-24 | No | NGRID | 2012-06-01
RI | 2012-06-01 | NEEWS (Rhode Island Reliability Project) | Kent County Substation Upgrades related to third 345/115 kV Autotransformer. | 1106 | 2008-09-24 | No | NGRID | 2012-05-01
RI | 2011-12-01 | NEEWS (Rhode Island Reliability Project) | South Wrentham 115kv terminal equipment upgrades | 1109 | 2008-09-24 | No | NGRID | 2012-12-01
VT | 2011-12-01 | West Rutland Capacitor Rebuild | Install two 115kV 25 MVAr capacitor banks at West Rutland to address low voltage concerns | 1171 | 2010-11-02 | NR | VELCO | 2012-03-01
VT | 2012-06-01 | Vermont Shunt Reactors | Install 345kV 60 MVAr shunt reactors (two at Coolidge and one at New Haven and relocate the New Haven reactor to Vernon) to address high voltage concerns | 1172 | 2011-03-23 | No | VELCO | 2011-12-01
VT | 2012-12-01 | LSP Jay Substation | Construct a new 4-breaker ring substation at Jay with two 115/46kV transformers | 1194 | 2011-02-07 | No | VELCO | 2012-10-01